## Sheet1
PYTHON BUDGET TRACKER - DEVELOPMENT LOG
Project: personal-budget-tracker
Language: Python 3.11
Repo: github.com/ericlambert-dev/budget-tracker (private)
Started: November 2025
FEATURE STATUS
Feature_ID | Feature_Name | Category | Status | Date_Started | Date_Completed | Notes
F-001 | Add income entry (amount, source, date) | Core | Complete | 2025-11-10 | 2025-11-14 | Working well. Input validated.
F-002 | Add expense entry (amount, category, date, note) | Core | Complete | 2025-11-10 | 2025-11-14 | Categories hardcoded for now.
F-003 | List all entries for current month | Core | Complete | 2025-11-15 | 2025-11-18 | Sorted by date. Looks clean.
F-004 | Calculate monthly net remaining | Core | Complete | 2025-11-18 | 2025-11-20 | Income minus expenses. Simple and correct.
F-005 | Persistent JSON storage | Core | Complete | 2025-11-20 | 2025-11-22 | budget_data.json. Survives restarts.
F-006 | Monthly summary view (category totals + % of income) | Display | In Progress | 2025-12-01 |  | Percentage math is off when income varies. Need to fix.
F-007 | Year-to-date rollup view | Display | Not Started |  |  | Planned after F-006 is done.
F-008 | CSV export | Export | Not Started |  |  | Easy once data model is solid. Low priority for now.
F-009 | Recurring entry support | Automation | Not Started |  |  | Would save a lot of manual entry. High priority after current sprint.
F-010 | Category budget threshold alerts | Alerts | Not Started |  |  | Nice to have. Not essential.
F-011 | ASCII bar chart for spending by category | Visualization | Not Started |  |  | Fun feature. After the core is solid.
F-012 | Multi-month comparison view | Display | Not Started |  |  | For when there are 3+ months of data. Not yet needed.
F-013 | Custom categories (user-defined) | Config | Not Started |  |  | Categories are hardcoded right now. Add config file later.
F-014 | argparse CLI argument handling | Refactor | Not Started |  |  | Currently using input() calls. argparse would be cleaner.
F-015 | Archive old months to separate file | Maintenance | Not Started |  |  | JSON grows without cleanup. Archive after 6 months of data.
BUG LOG
Bug_ID | Date_Found | Description | Severity | Status | Resolution
B-001 | 2025-11-22 | Date parsing fails on MM/DD/YYYY input | Medium | Open | Need format detection or force ISO format with better command format
B-002 | 2025-11-28 | JSON file grows without cleanup - old months pile up | Low | Open | Will fix with F-015 archive feature
B-003 | 2025-12-05 | Monthly percentage calc wrong when two income sources in same month | Medium | Open | Logic error in summary function - average vs total issue
B-004 | 2025-12-10 | Category names are case-sensitive, groceries != Groceries | Low | Open | Normalize to lowercase on input
B-005 | 2026-01-15 | App crashes if budget_data.json is deleted or corrupted | High | Open | Add graceful error handling and auto-recreate if missing
B-006 | 2026-02-01 | List view truncates long notes in the terminal output | Low | Open | Add wrapping or truncation with ellipsis
COMMIT HISTORY (abbreviated)
Date | Commit_Message | Files_Changed
2025-11-14 Initial commit: add income and expense entry | main.py, budget_data.json
2025-11-18 Add list view sorted by date | main.py
2025-11-20 Add monthly net remaining calculation | main.py
2025-11-22 Add persistent JSON storage | main.py, data_handler.py
2025-12-01 Start monthly summary view, WIP | main.py, summary.py
2025-12-10 Fix category input validation | main.py
2026-01-15 Refactor data model to list of dicts | data_handler.py
2026-01-22 Add basic error messages for invalid input | main.py
2026-02-05 Partial fix for percentage calc | summary.py
2026-02-20 Add note field to expense entries | main.py, data_handler.py
NEXT SESSION PLAN
1. Fix B-003 (percentage calculation bug in summary.py)
2. Fix B-005 (crash on missing/corrupted JSON)
3. Complete F-006 (monthly summary view with corrected percentages)
4. Start F-009 (recurring entries)
PROJECT NOTES
- No external dependencies yet. Stdlib only (json, datetime, os, argparse planned)
- HP Pavilion 15, Python 3.11, VS Code
- Tests: None yet. Should add unittest before the feature set grows further.
- Mateo asked if he can use it. Might add multi-user support eventually,
or just build a simple Flask version later as a learning project.