## Budget
FIVE ELEMENTS, Production Budget
Premiere: Chennai Arts Festival, December 2026 ¦ Target budget Rs 8,00,000 ¦ Updated 10 February 2026
Category | Item | Estimated (Rs) | Committed (Rs) | Status
Costumes | Eight troupe costumes, design and tailoring | 1,80,000 | 1,10,000 | In progress, Fire fabric being changed
Costumes | Footwear, hard and soft shoe, 8 dancers | 60,000 | 60,000 | Ordered
Music | Patrick Doyle, bodhran, rehearsals and run | 70,000 | 35,000 | Advance paid
Music | Aoife Brennan, voice | 70,000 | 35,000 | Advance paid
Music | Colm Fitzgerald, fiddle, special movements + travel | 90,000 | 20,000 | Residency Nov, travel from Pondicherry
Projection | Digital projection design, Air and Ether | 90,000 | 40,000 | Shared language with Metro commission
Projection | Equipment hire and operator, festival run | 45,000 | 0 | To confirm with festival tech
Venue | Tech rehearsals and additional calls | 35,000 | 0 | Per festival schedule
Production | Lighting design collaboration | 50,000 | 0 | Quotes pending
Production | Stage management and crew | 30,000 | 0
Marketing | Programme, photography, promo film | 25,000 | 10,000 | Photographer booked
Contingency | Reserve, 10 percent | 55,000 | 0 | Held
Total estimated |  | 8,00,000 | 3,10,000
Funding: academy reserve plus Chennai Arts Festival fee, grant application submitted (see grant file).