## Sprint Log
Sprint | Start Date | End Date | Epic | Story ID | Description | Assignee | Points | Status | Notes
S12 | 2026-10-01 | 2026-10-14 | Export and Sharing | NS-F001 | CSV export endpoint | Alex Park | 3 | Done | see P01 for full PRD
S12 | 2026-10-01 | 2026-10-14 | Analytics Core | NS-F002 | Date range filter UI | Dana Cruz | 5 | Done | see P01 for full PRD
S12 | 2026-10-01 | 2026-10-14 | Export and Sharing | NS-F003 | Shared dashboard link token | Priya Nair | 8 | In progress | see P01 for full PRD
S13 | 2026-10-15 | 2026-10-28 | Export and Sharing | NS-F003 | Shared dashboard link token | Priya Nair | 8 | In progress | see P01 for full PRD
S13 | 2026-10-15 | 2026-10-28 | Analytics Core | NS-F005 | User-level drill-down query | Ryan Iyer | 5 | Done | see P01 for full PRD
S13 | 2026-10-15 | 2026-10-28 | Analytics Core | NS-F006 | Funnel visualization chart | James Okafor | 8 | In progress | see P01 for full PRD
S14 | 2026-10-29 | 2026-11-11 | Analytics Core | NS-F006 | Funnel visualization chart | James Okafor | 8 | In progress | see P01 for full PRD
S14 | 2026-10-29 | 2026-11-11 | Analytics Core | NS-F007 | Cohort comparison table | Dana Cruz | 5 | Backlog | see P01 for full PRD
S14 | 2026-10-29 | 2026-11-11 | Notifications | NS-F004 | Email digest scheduler | Alex Park | 3 | Backlog | see P01 for full PRD
S14 | 2026-10-29 | 2026-11-11 | Notifications | NS-F010 | the messaging platform alert webhook | Priya Nair | 3 | Backlog | see P01 for full PRD

## Velocity
Sprint | Planned Points | Completed Points | Velocity
S10 | 28 | 24 | 86%
S11 | 30 | 28 | 93%
S12 | 32 | 30 | 94%
S13 | 30 | 28 | 93%