# Northstar Sprint 14 Retrospective

Growth and Analytics Pod | October 29 to November 11, 2026 | Doc ID: D01

## 1. Sprint Overview

Sprint 14 was the final development sprint before the Northstar GA launch on November 13, 2026. The sprint delivered the remaining three features in scope: NS-F004 Email Digest Reports, NS-F010 Messaging Alert Integration, and NS-F007 Cohort Comparison Table. All three features are now in production and verified by the respective pilot accounts. Sprint velocity was 28 of 30 planned points (93 percent). Two points rolled to hypercare backlog (minor UI polish on the messaging platform alert configuration UI). See X02.xlsx sprint log for full story breakdown.

## 2. What Went Well

NS-F007 Cohort Comparison Table shipped ahead of internal deadline (November 7 vs November 9 target). Priya Shankar at Atlas Growth Labs gave it a 5-star rating in the cycle 4 feedback form.

No critical bugs or P1 incidents during the sprint. the error-tracking tool error rate stayed under 0.1 percent for all 14 days.

Megan Shaw's decision to isolate the the messaging webhook into a separate microservice proved correct: load testing showed the main analytics service was unaffected by high alert volumes.

Daily async standup format (a messaging thread) worked well during the compressed October schedule. Team maintained velocity despite multiple external life events.

The pilot account sign-off process (all three accounts signed by November 8) went smoothly. Advance preparation of the sign-off checklist in X12.xlsx freeze section paid off.

## 3. What Could Be Improved

The email digest scheduler (NS-F004) required a last-minute backend change when we discovered the job queue was not idempotent under retry. This should have been caught in the technical design review in Sprint 12. Recommendation: add a dedicated idempotency checklist item to the technical design template.

Ryan Iyer's data pipeline work for the cohort comparison was blocked for 1.5 days on a missing the event pipeline schema change. The dependency was in the sprint plan but not flagged as a blocker risk. Better dependency flagging in sprint planning would have surfaced this earlier.

The sprint review demo was underprepared. Tomoko had the designs ready but the demo environment had a stale data seed. Recommend a dedicated 30-minute demo environment check the day before sprint review.

My own availability during October 15 to 19 (annual physical, wedding) created a 4-day gap that Megan covered well but which required extra async communication. Future planned absences should have a named deputy explicitly announced at sprint planning, not assumed.

## 4. Action Items

| # | Action | Owner | Due |
| --- | --- | --- | --- |
| A1 | Add idempotency checklist to technical design template in the documentation tool | Megan Shaw | Nov 20, 2026 |
| A2 | Update sprint planning template: dependency risk column | Stephanie Wells | Nov 20, 2026 |
| A3 | Add 30-min demo env check to sprint review agenda in the project tracker | Ryan Iyer | Nov 20, 2026 |
| A4 | Document PM deputy process in the team working agreement | Stephanie Wells | Nov 25, 2026 |
| A5 | Resolve remaining 2 points (the messaging platform UI polish) in hypercare backlog | Dana Cruz | Nov 20, 2026 |

## 5. Sprint Metrics

| Metric | Value | Notes |
| --- | --- | --- |
| Planned story points | 30 |  |
| Completed story points | 28 | 93 percent velocity |
| Rolled to next sprint | 2 | the messaging platform UI polish, minor only |
| Bug count opened | 3 | All P2 or lower |
| Bug count closed | 4 | 1 carryover from S13 |
| PR count | 42 | 14-day sprint |
| Avg PR merge time | 18 hours | Target was 24 hours |
| the error-tracking tool P95 error rate | 0.08% | Well below 0.5% SLO |

## 6. Team Shoutouts

Megan Shaw: held the engineering team together through a compressed calendar and delivered a clean sprint. The microservice call on NS-F010 was the right architectural choice.

James Okafor: personally drove the Safari memory leak fix from detection to production in under 18 hours. This cleared the last blocker for ENT-PC-002 sign-off.

Tomoko Hayashi: the funnel visualization (NS-F006) design revisions based on pilot feedback were thoughtful and fast. Kate Ellison specifically called out the chart clarity in her NPS comment.

Ryan Iyer: the the event pipeline schema fix that unblocked the cohort comparison pipeline was a weekend effort. Appreciated.

## 7. Next Steps: Hypercare and Post-Launch

Sprint 15 is officially the 14-day hypercare period (November 13 to November 27, 2026). The team is on a doubled on-call rotation. Stephanie returns to full availability after November 17. The first retrospective after launch will be scheduled for November 28, 2026. Post-launch feature development begins in Sprint 16 (December 2026) with NS-F009 benchmark overlay scoping. See P09.pdf launch readiness report and X12.xlsx for post-launch backlog.

## 8. Appendix: Story Summary

| Story ID | Title | Points | Assignee | Final Status |
| --- | --- | --- | --- | --- |
| NS-F004 | Email digest scheduler | 8 | Alex Park | Done |
| NS-F010 | messaging alert integration | 5 | Priya Nair | Done |
| NS-F007 | Cohort comparison table | 8 | Dana Cruz + Ryan Iyer | Done |
| NS-UI-07 | the messaging platform config UI polish | 2 | Dana Cruz | Rolled to hypercare |
| NS-BUG-14a | Safari memory leak fix | 3 | James Okafor | Done |
| NS-BUG-14b | Idempotency retry fix | 2 | Alex Park | Done |