## RICE Prioritization
Feature ID | Feature Name | Reach | Impact (1-3) | Confidence (%) | Effort (weeks) | RICE Score | Sprint Target | Pilot Demand | Status | Notes
NS-F001 | Export to CSV | 8000 | 3 | 0.9 | 2 | 10800 | S12 | ENT-PC-001, ENT-PC-002 | Done | MVP export, delivered Oct 2026
NS-F002 | Custom date range filter | 7500 | 2 | 0.8 | 1 | 12000 | S12 | ENT-PC-003 | Done | see X07 cycle 2
NS-F005 | User-level drill-down | 5500 | 3 | 0.9 | 3 | 4950 | S12 | ENT-PC-002 | Done | performance optimized
NS-F003 | Shared dashboard links | 6200 | 2 | 0.7 | 2 | 4340 | S13 | ENT-PC-001 | In progress | launch token MVP
NS-F006 | Funnel visualization | 4900 | 2 | 0.7 | 3 | 2286.7 | S13 | All pilots | In progress
NS-F004 | Email digest reports | 5800 | 2 | 0.6 | 2 | 3480 | S14 | ENT-PC-001 | Backlog
NS-F010 | messaging alert integration | 2900 | 2 | 0.7 | 2 | 2030 | S14 | ENT-PC-002 | Backlog
NS-F007 | Cohort comparison table | 4600 | 3 | 0.8 | 3 | 3680 | S14 | ENT-PC-003 | Backlog
NS-F008 | Annotation layer | 3800 | 1 | 0.5 | 2 | 950 | Post-launch | ENT-PC-001 | Deferred | low pilot demand
NS-F009 | Benchmark overlay | 3200 | 2 | 0.6 | 3 | 1280 | Post-launch | All pilots | Backlog
NS-F011 | API access for enterprise | 2600 | 3 | 0.5 | 6 | 650 | Post-launch | ENT-PC-003 | Post-launch | Q1 2027
NS-F012 | White-label branding | 2100 | 1 | 0.4 | 5 | 168 | Post-launch | ENT-PC-003 | Post-launch | Q2 2027

## Freeze Checklist
Feature freeze date | October 9, 2026
Items in scope for ship | NS-F001, NS-F002, NS-F003, NS-F004, NS-F005, NS-F006, NS-F007, NS-F010
Items deferred post-launch | NS-F008, NS-F009, NS-F011, NS-F012
Pilot sign-off needed from | ENT-PC-001 Kate Ellison, ENT-PC-002 Marcus Webb, ENT-PC-003 Priya Shankar
Engineering lead | Megan Shaw, megan.shaw@gmail.com
PM owner | Stephanie Wells, see P01 for full PRD
Ship target | November 13, 2026
See also | X02 sprint log, P01 PRD, P09 launch readiness, X07 pilot feedback