# Wedding Master Planning Document

Stephanie Wells and Matt Collins | October 17, 2026 | Doc ID: D02

## 1. Overview

This document is the single source of truth for the wedding on October 17, 2026 at Redwood Glen Estate, Woodside, CA. It covers vendor contacts, timeline, checklist, budget reference, and guest management. Wedding planner: Lena Choi, Serafina Events, lena.choi@gmail.com, (650) 555-0312. Budget tracked in X03.xlsx. Contract summary in P04.pdf.

## 2. Vendor Directory

| Vendor | Category | Contact | Phone / Email | Status |
| --- | --- | --- | --- | --- |
| Redwood Glen Estate | Venue | Events team | events@redwoodglen.com | Confirmed |
| Serafina Events / Lena Choi | Coordinator | Lena Choi | lena.choi@gmail.com, (650) 555-0312 | Active |
| Harvest Table Co. | Catering | Marcus Lin | catering@harvesttable.com | Confirmed |
| Jordan Torres | Photography | Jordan Torres | jordan.torres@gmail.com, (415) 555-0173 | Confirmed |
| Bloom and Stem SF | Florals | Priya Kapoor | bloom.stem.sf@gmail.com | Confirmed |
| Coast String Quartet | Music | Maya Chen | coaststring@gmail.com | Confirmed |
| Companion Bakehouse | Cake | Sam Rivera | hello@companionbake.com | Confirmed |
| a bridal boutique | Attire | Stylist team | bhldn.sf@gmail.com | Ordered |
| DJ Max Ortega | Reception DJ | Max Ortega | max.ortega@djmax.com | Confirmed |

## 3. Master Checklist

### 3.1 Completed (before October 2026)

Venue booked: Redwood Glen Estate deposit paid January 20, 2026.

Wedding coordinator engaged: Serafina Events, deposit $3,000 paid January 20, 2026.

Catering contract signed: Harvest Table Co., vegetarian menu, 80 guests.

Photography booked: Jordan Torres, 7-hour coverage, contract signed January 28, 2026.

Florist engaged: Bloom and Stem SF, ceremony and tables.

Music: Coast String Quartet, ceremony and cocktail hour.

Cake ordered: Companion Bakehouse, four-tier.

Invitations mailed: an invitation service, 90 invitations sent February 14, 2026.

Dress ordered: a bridal boutique.

Wedding website live: a website builder, stephandmatt2026.com.

Honeymoon cabin: Mendocino coast cabin reserved.

### 3.2 October 2026 Remaining Tasks

| Task | Due Date | Owner | Status |
| --- | --- | --- | --- |
| Final guest count to Harvest Table Co. | October 1, 2026 | Stephanie | Due |
| Balance payment to Serafina Events ($2,000) | October 1, 2026 | Stephanie + Matt | Due |
| Venue balance payment | October 1, 2026 | Stephanie + Matt | Due |
| Final venue walkthrough with Lena Choi | October 10, 2026 | All vendors | Scheduled |
| Dress final fitting | October 5, 2026 | Stephanie | Scheduled |
| Vow draft exchange with Matt | October 5, 2026 | Both | Pending |
| Bridal party briefing (Sarah, Tara, Jordan) | October 12, 2026 | Stephanie | Pending |
| Dad's accessibility seating confirmed with venue | October 1, 2026 | Stephanie | Due |
| Groom party logistics (Matt) | October 10, 2026 | Matt | Pending |
| Wedding day emergency kit packed | October 15, 2026 | Stephanie | Pending |

## 4. Day-of Timeline

| Time | Activity | Detail |
| --- | --- | --- |
| 10:00 AM | Vendor arrival | Flowers, catering, string quartet soundcheck |
| 12:30 PM | Bridal party prep | Hair and makeup at venue |
| 1:30 PM | Bridal party ready | First look with Matt |
| 2:00 PM | Ceremony begins | Officiant: Rev. Kim Park |
| 2:45 PM | Ceremony ends | Guests proceed to cocktail area |
| 3:00 PM | Cocktail hour | String quartet plays, catering circulates |
| 4:00 PM | Reception doors open | Guests seated |
| 4:30 PM | First dances | Stephanie and Matt, then family |
| 5:00 PM | Dinner service | Harvest Table vegetarian buffet |
| 6:30 PM | Toasts | Sarah Brennan, Kyle Wells, Tara Collins, Matt |
| 7:00 PM | Cake cutting |  |
| 7:30 PM | Dancing opens | DJ Max Ortega |
| 9:30 PM | Last song | Guest departure starts 10 PM |
| 10:00 PM | Event ends | Vendors wrap, venue cleared by 11 PM |

## 5. Bridal Party Contact List

| Name | Role | Phone | Notes |
| --- | --- | --- | --- |
| Sarah Brennan | Maid of honor (Stephanie) | (415) 555-0158 | Holds emergency kit |
| Tara Collins | Maid of honor (Matt's side) | (310) 555-0267 | Travels from LA Oct 15 |
| Jordan Torres | Bridesmaid and photographer | (415) 555-0173 | Photo setup 9 AM |
| Kyle Wells | Best man | (206) 555-0216 | Arrives Oct 14 from Seattle |

## 6. Accessibility and Special Notes

Robert Wells (father of bride, Parkinson's Stage 2): reserved front-row aisle seat, accessible parking arranged with venue. Linda Wells (mother) will assist. Stephanie will confirm grab-bar availability in venue restrooms with Lena Choi.

Vegetarian diet: all catering is vegetarian. Vegan option available on request. Gluten-free option available.

Guest with nut allergy (see X10.xlsx guest list row): caterer notified.

Honeymoon: Mendocino coast cabin, November 14 to 21, 2026. Cabin address shared with Matt only.

## 7. Budget Quick Reference

Full budget is in X03.xlsx. Total budget $45,000. Saved: $38,000 (Stephanie and Matt $18,000 + Matt's parents $15,000 + Stephanie's parents $5,000). Contract summary in P04.pdf (Serafina Events).

## 8. Emergency Contact Plan (Wedding Day)

If any vendor does not arrive by 30 minutes after their scheduled time, call Lena Choi first, then the vendor directly. For a medical emergency, call 911; Lena Choi holds the venue first-aid kit. Matt's contact: (415) 555-0142. For Robert Wells (Dad) specifically, Linda Wells (510) 555-0193 is the first call. Nearest hospital to Redwood Glen: Stanford Hospital, Palo Alto, 5 miles.