WAIKIKI REEF SUNRISE WALK - EVENT PLANNING NOTES

December 20, 2025 | 6:00 AM - 8:30 AM

Lead Organizer: Surfrider Foundation Hawaii

Co-presenter: Pacific Reef Research Institute (Angela Peterson)

Last updated: December 15, 2025

LOGISTICS

Gather time: 5:45 AM at Waikiki Beach east end (near Queens surf break)

Angela arrives: 5:30 AM (early setup with Jade)

Jade Reyes (PRRI table): 5:30 AM

Walk route: east to west along shoreline, Surfrider team leads

Duration: approx 2.5 hours (ends ~8:30 AM)

Expected attendance: 600-800 (Surfrider's last similar event drew 650)

ANGELA'S 10-MINUTE REMARKS - OUTLINE

Slot: 6:15 AM (after Surfrider welcome; before walk begins)

1. Opening (1 min): Waikiki reef as a living system, not just scenery

People swim above it every day; most don't know what's down there

2. The data (3 min): 40+ years of temperature increase in Hawaiian nearshore waters

Phase III monitoring context; what PRRI does

Station C November bleaching flag - what it means for Waikiki reef health

3. What you can do (4 min):

Reef-safe sunscreen (no oxybenzone/octinoxate)

Avoid touching or standing on coral

Support Surfrider; sign up for PRRI newsletter

Come to the February reef walk at Hanauma Bay

4. Close (2 min): Gratitude; reef needs witnesses not just scientists

PRRI TABLE (Jade Reyes staffing)

Materials:

Coral ID laminated cards: 20 copies

Station C bleaching fact sheet: 50 copies (Angela printing Dec 18)

PRRI tri-fold brochure: 40 copies

Newsletter sign-up sheets: 8 sheets on clipboard

Reef-safe sunscreen samples: 30 (Hana Hou partnership; Jade to pick up Dec 19)

Target: 30+ newsletter signups

COORDINATION WITH SURFRIDER HI

Contact: Camille Tanaka (events lead) - permits and beach logistics

Shared social media post: Surfrider tagging PRRI handle (Angela to review Dec 17)

Cleanup bags: Surfrider providing; PRRI not needed

Hawaii Wildlife Fund: also tabling; separate table

POST-EVENT TASKS

Jade: email newsletter signups to PRRI comms list by December 22

Angela: write brief event recap for Q1 quarterly report (due January 15, 2026)

Follow-up: Hanauma Bay reef walk - schedule for February 2026