## Slide 1
PEAK PERFORMANCE PT
Sports Performance Lab
Buildout Status and Launch Plan
Owner review, prepared February 2026

## Slide 2
WHERE WE STAND
Budget and Schedule at a Glance
$120,000
Total project budget
$52,000
Spent to date
$68,000
Remaining
October
Target opening
Capital project tracked separately from clinic operating figures
Demolition of the old storage suite complete, framing underway
Flooring locked, a poured rubber surface rated for the plate system
Peak Performance PT | Performance Lab Buildout

## Slide 3
THE STACK
Testing Equipment
Item | Vendor | Quote USD | Status
Force plate system | VALD Performance | 18,000 | Approved
Hamstring testing, NordBord | VALD Performance | 9,500 | Approved
Anti gravity treadmill | AlterG dealer | 35,000 | Approved
Performance testing hub | VALD Performance | 12,000 | Pending final quote
Total, four systems |  | 74,500 | Three approved
Combined insured value reported to the property carrier

## Slide 4
THE PLAN
Path to Open House
February 20, demolition finished, framing for the testing bay begins
Rough electrical staged for the force plate pit and the AlterG circuits
October 9, substantial completion targeted
Week of October 12, equipment delivery and install
Following week, staff training and a soft open
Late October, community open house and athlete showcase
The covered patio at the house follows, same crew

## Slide 5
THE NUMBERS
Where the Budget Goes
Chart: 
| Construction | Force plate | AlterG | VALD hub | NordBord
USD thousands | 45.5 | 18 | 35 | 12 | 9.5
Equipment financed under SBA 7a, construction from operating capital

## Slide 6
FINANCING
Equipment Loan Terms
$74,500
Loan amount
7.10%
Fixed rate
120 mo
Term
$868.85
Monthly
SBA 7a equipment financing, best rate of four lenders quoted
Estimated total interest 29,762.50 over the life of the loan
First payment November 2026, aligned with equipment install
Preliminary terms, reconfirmed at closing

## Slide 7
From feel to numbers.
Objective testing behind every return to play decision.
Next step, confirm the slab recess with VALD before electrical is closed in.