## Slide 1
Spring Forum on Advising
Planning brief and run of show
Hosted by the Student Association, Academic Affairs Committee
Prepared by Brian Patterson, Vice President of Academic Affairs

## Slide 2
The goal
Give students one honest hour on advising and course planning, then turn the most common gaps into a short list the faculty senate can act on.
Who it serves undergraduates choosing a path, especially first and second years
What success looks like a packed room and three concrete recommendations
Academic Affairs Committee
2

## Slide 3
Timeline
Oct 26, 2026
Planning meeting
Lock the date and confirm Goldstein Auditorium
Nov 2026
Panel invitations
Advising office and two faculty advisors
Jan 2027
Promotion
Flyers, residence halls, and the events page
Feb 2027
Forum
The event, with notes taken for the senate brief
Mar 2027
Recommendations
Short list delivered to the faculty senate
3

## Slide 4
Budget at a glance
$945
Total income
$800
Total expenses
$145
Balance held
Largest line is the speaker travel stipend at $350. Refreshments at $210 keep the room full to the last question. The balance carries to the next committee event.
4

## Slide 5
Volunteer roles
Role | Slot | Needed | Signed up
Setup | 4:30 to 5:30 PM | 4 | 4
Greeting and sign in | 5:15 to 6:00 PM | 3 | 3
Microphone runner | 5:30 to 7:00 PM | 2 | 2
Refreshments | 5:00 to 7:00 PM | 3 | 2
Note taking | 5:30 to 7:00 PM | 2 | 2
Cleanup | 7:00 to 7:45 PM | 4 | 3
18 slots, 16 filled. Two open: one refreshments, one cleanup.
5

## Slide 6
Run of show
5:30 PM
Doors and sign in
5:45 PM
Welcome and the three priorities
6:00 PM
Advising panel
6:35 PM
Open questions from the floor
6:55 PM
Wrap and how to stay involved
7:00 PM
Close and cleanup
6

## Slide 7
Stop by, or shape it with us.
Academic affairs desk, Schine Student Center . the committee meets every other Monday