## Slide 1
EVENT OPERATIONS PLAN
Veterans Day Fish Fry
American Legion Post 99, Brooksville, Wednesday November 11, 2026.
Carlos Bennett on lead fry, with the Post 99 auxiliary

## Slide 2
ON THIS DECK
What is inside
Post 99 Fish Fry
02 / 10
1
The event
What we are putting on
2
The menu
Fried fish and the fixings
3
Run of show
Setup to last plate
4
Crew and roles
Who does what
5
Sourcing
Fish and quantities
6
Proceeds
Where the money goes

## Slide 3
THE EVENT
Veterans Day fish fry
Post 99 Fish Fry
03 / 10
Nov 11
Wednesday
4:30 PM
Doors open
5:00 to 7:30
Serving
~120
Plates
The plan
• Held at the Post 99 hall, 1450 Howell Avenue
• Carlos on lead fry, two fryers running
• Auxiliary handles hush puppies, slaw, and grits
• Setup starts at 2:00 PM
The tradition
• Donated fish fry, annual since 2017
• Proceeds go to the veterans relief fund
• The fish fry keeps the hall full
• Diane helps plate the line

## Slide 4
ON THE PLATE
The menu
Post 99 Fish Fry
04 / 10
Fried grouper and mullet
Lead fry, cornmeal crust, hot from the fryer
Hush puppies
Auxiliary, fried in small batches
Coleslaw
Cool, crisp, made the morning of
Stone ground grits
Held hot on the burner
Sweet tea and lemonade
By the gallon
Peach cobbler
Dessert table, donated

## Slide 5
RUN OF SHOW
Setup to last plate
Post 99 Fish Fry
05 / 10
2:00 PM
Setup
Fryers, tables, and the serving line in place
3:30 PM
Oil up
Bring the fryers to temperature, stage the fish
4:30 PM
Doors
Doors open, sweet tea poured
5:00 PM
Serving
Plates moving, two fryers running steady
7:30 PM
Last plate
Wind down, break the line, clean the fryers

## Slide 6
WHO DOES WHAT
Crew and roles
Post 99 Fish Fry
06 / 10
Lead fry
Carlos
Runs both fryers, calls the fish
Second fryer
Post volunteer
Hush puppies and second batches
Sides
Auxiliary
Slaw, grits, and the dessert table
Serving line
Diane and team
Plating and keeping the line moving
Setup
Post crew
Tables, fryers, and the hall
Cleanup
All hands
Break down, oil out, sweep

## Slide 7
SOURCING
Fish and quantities
Post 99 Fish Fry
07 / 10
Item | Quantity | Source
Grouper fillets | 35 lbs | Co-op, Tuesday pickup
Mullet fillets | 25 lbs | Co-op, Tuesday pickup
Cornmeal and flour | 20 lbs | Donated
Fryer oil | 6 gallons | Donated
Hush puppy mix | 12 lbs | Auxiliary
Slaw and grits | For 120 | Auxiliary
60 lbs
Total fish
~120
Plates planned
Tue
Pickup day

## Slide 8
WHERE IT GOES
Proceeds and budget
Post 99 Fish Fry
08 / 10
Chart: 
| Veterans relief fund | Supplies recovered | Hall and utilities
Proceeds | 70 | 20 | 10
The point of it
• Most of every plate goes to the relief fund
• Donated fish and oil keep costs low
• A small share covers the hall and utilities
• Carlos donates the labor and the know how
• Annual since 2017, and the hall counts on it

## Slide 9
IF IT RAINS
Safety and contingency
Post 99 Fish Fry
09 / 10
Weather
• Fryers stage under the covered side entrance
• Serving moves fully indoors if needed
• Tea and dessert tables inside either way
Fry safety
• Fryers roped off from foot traffic
• Extinguisher rated for oil on hand
• Oil cooled fully before any move
If charter fills
• Carlos flags the week early
• Second fry lead briefed as backup
• Post crew can run the line

## Slide 10
THANK YOU
Plates up for the veterans
American Legion Post 99, Brooksville. Wednesday November 11, 2026, serving 5:00 to 7:30 PM.
Questions, reach Carlos at (352) 555-0144