## Project Phases
Phase | Task | Start_Date | Due_Date | Status | Assigned_To | Notes
Research | Review museum brief and specifications | 2026-01-28 | 2026-02-07 | Complete | Grace Hatfield | Received brief Jan 28
Research | Photograph source quilts at Stoneridge collection | 2026-02-10 | 2026-02-14 | Complete | Grace Hatfield | 2 visits to museum
Design | Create pattern mockups in Figma | 2026-02-15 | 2026-02-28 | Complete | Grace Hatfield | Log cabin variation selected
Design | Submit design for museum approval | 2026-10-01 | 2026-10-08 | Scheduled | Grace Hatfield | Submit mockups for museum approval
Materials | Order primary fabrics from Cotton Patch | 2026-10-09 | 2026-10-16 | Scheduled | Grace Hatfield | Order CPQ-2026-0204
Materials | Order batting and backing | 2026-10-16 | 2026-10-23 | Scheduled | Grace Hatfield | Order CPQ-2026-0204 incl. batting
Construction | Cut all fabric pieces | 2026-10-26 | 2026-11-06 | Scheduled | Grace Hatfield | 1,440 pieces cut
Construction | Piece quilt top - log cabin blocks (24 blocks) | 2026-11-06 | 2026-11-13 | Scheduled | Grace Hatfield | Top assembled
Construction | Baste quilt top, batting, and backing | 2026-11-13 | 2026-11-18 | Scheduled | Grace Hatfield | Begin construction phase
Construction | Hand quilt main body | 2026-11-18 | 2026-11-30 | Scheduled | Grace Hatfield | Estimated 40 hours
Finishing | Bind and label | 2026-11-30 | 2026-12-04 | Scheduled | Grace Hatfield | Include museum provenance label
Delivery | Final inspection and photography | 2026-12-05 | 2026-12-06 | Scheduled | Grace Hatfield | Before shipping
Delivery | Ship via UPS to Stoneridge Museum | 2026-12-07 | 2026-12-08 | Scheduled | Grace Hatfield | UPS insured - ref SRF-2026-0047
Completion | Invoice final payment (50%) | 2026-12-09 | 2026-12-09 | Scheduled | Grace Hatfield | $900 final payment on delivery

## Materials Budget
Item | Vendor | Estimated_Cost | Actual_Cost | Order_Number | Status
Kona Cotton - Creams (10 yd) | Cotton Patch Quilt Supply | 84.90 | 84.90 | CPQ-2026-0204 | To Order
Kona Cotton - Blues (8 yd) | Cotton Patch Quilt Supply | 67.92 | 67.92 | CPQ-2026-0204 | To Order
Kona Cotton - Earthy Tones (6 yd) | Cotton Patch Quilt Supply | 50.94 | 50.94 | CPQ-2026-0204 | To Order
Reclaimed Flannel Bundle | Cotton Patch Quilt Supply | 42.00 | 42.00 | CPQ-2026-0061 | To Order
Quilters Dream Batting - Queen | Cotton Patch Quilt Supply | 29.95 | 29.95 | CPQ-2026-0118 | To Order
Backing Fabric Muslin 60in (8 yd) | Cotton Patch Quilt Supply | 47.92 | 47.92 | CPQ-2026-0157 | To Order
Gutermann Thread - Ecru (6 spools) | Cotton Patch Quilt Supply | 20.94 | 20.94 | CPQ-2026-0204 | To Order
Hand Quilting Needles | Cotton Patch Quilt Supply | 8.99 | 8.99 | CPQ-2026-0241 | To Order
Museum Provenance Label (embroidered) | Local Embroidery - Syracuse | 25.00 |  | Pending | To Order
UPS Insured Shipping | UPS | 45.00 |  | Pending | To Order
TOTAL |  | 423.56 | 353.56