## Timeline
Sensory Play Resource Guide, Project Plan
Author: Jennifer Long, OTR/L Target manuscript: December 2026
Phase | Owner | Start | Target Finish | Status
Activity drafting (40 total) | Jennifer | 2025-08-01 | 2026-11-15 | 18 of 40 drafted
Developmental targets review | Jennifer | 2025-10-01 | 2026-11-30 | In progress
Illustrations (line art) | Helen Carter | 2026-10-12 | 2027-01-31 | Contract signed
Parent handout appendix | Jennifer | 2026-10-01 | 2026-12-15 | Started
Internal clinical review | Dr. Amy Ross | 2026-12-01 | 2027-01-15 | Scheduled
Publishing decision (KDP vs AOTA) | Jennifer | 2026-11-01 | 2026-12-31 | Comparing
Final manuscript assembly | Jennifer | 2027-01-15 | 2027-02-28 | Not started
Budget Item |  | Estimate | Committed
Illustrations (Helen Carter) |  | 3000 | 3000
Self publishing setup (KDP/IngramSpark) |  | 450 | 0
Editing pass (freelance) |  | 1200 | 0
Cover design |  | 600 | 0
Sample print proofs |  | 180 | 0
Total |  | 5430 | 3000