# Thread & Bone, Issue 7

Editorial plan and production notes  |  Target release: November 2026

Editor and maker: Jennifer Williams. Layout in Canva. Print run via Fox Point Copy. Distribution to Symposium Books, Books on the Square, and the Etsy shop.

## Theme

Inventory. What we count, what counts us. Poems and short prose about the small ledgers of a life, money, hours, groceries, the running tallies we keep without meaning to.

## Contents, in order

| Page | Piece | Contributor | Note |
| --- | --- | --- | --- |
| 1 | Opening note | Jennifer | Half page, written last |
| 2 | Fox Point Inventory | Jennifer | Lead poem, full page |
| 3 | Three short poems | Dex Morales | Solicited, due Oct 20 |
| 4 | What the Tip Jar Knows | Jennifer | Pairs with the cover image |
| 5 | Guest essay, on thrift | Nia Okafor | 800 words, first time contributor |
| 6 | Found poem from a receipt | Jennifer | Visual piece, scanned |
| 7 | Back cover, colophon | Jennifer | Pricing and credits |

## Schedule

Oct 13, contributor pieces solicited, deadline set for Oct 20.

Oct 24, full draft assembled in Canva.

Oct 28, proof printed and read aloud with Dex over coffee.

Nov 2, corrections, final export to PDF.

Nov 6, print run of 60 copies.

Nov 9, release, drop copies at the two shops, list on Etsy.

Print budget capped at the 30 dollar monthly zine fund plus carryover. See the print run cost sheet.