## Hendricks Budget
Spencer Interiors
Hendricks Residence, Paradise Valley ¦ Project SI-2024-H01
Budget tracker as of February 27, 2026 ¦ Target completion October 2026
Category | Budget | Committed | Spent to Date | Remaining | Percent Spent
Furniture and seating | 62000 | 52000 | 38000 | 24000 | 61.29%
Stone and tile | 54000 | 49000 | 41000 | 13000 | 75.93%
Lighting | 22000 | 18000 | 14000 | 8000 | 63.64%
Textiles and rugs | 28000 | 20000 | 12000 | 16000 | 42.86%
Cabinetry and millwork | 48000 | 44000 | 32000 | 16000 | 66.67%
Appliances | 24000 | 22000 | 18000 | 6000 | 75%
Window treatments | 16000 | 9000 | 6000 | 10000 | 37.5%
Paint and finishes | 12000 | 10000 | 8000 | 4000 | 66.67%
Labor and install | 40000 | 30000 | 14000 | 26000 | 35%
Design fee | 10000 | 6000 | 4000 | 6000 | 40%
Contingency | 4000 | 0 | 0 | 4000 | 0%
Total | 320000 | 260000 | 187000 | 133000 | 58.44%
Note: Custom Calacatta Viola marble for the master bath is on order at 28,000 within Stone and tile.