## Martin Condo Budget
Spencer Interiors
Martin Condo, Downtown Phoenix ¦ Project SI-2025-M02
Budget tracker as of February 26, 2026 ¦ Client Sarah Martin
Category | Budget | Spent to Date | Remaining | Percent Spent
Furniture and seating | 32000 | 21768 | 10232 | 68.03%
Lighting | 8000 | 2360 | 5640 | 29.5%
Textiles and rugs | 9000 | 3200 | 5800 | 35.56%
Window treatments | 7000 | 1800 | 5200 | 25.71%
Stone and tile | 9000 | 6500 | 2500 | 72.22%
Paint and finishes | 5000 | 2400 | 2600 | 48%
Labor and install | 9000 | 2972 | 6028 | 33.02%
Design fee | 4000 | 1000 | 3000 | 25%
Contingency | 2000 | 0 | 2000 | 0%
Total | 85000 | 42000 | 43000 | 49.41%
Furniture spend reflects the selected vendor mix from the trade pricing comparison.