Sepsis Care Quality Initiative, Summary Report

Prepared February 15, 2026. Covers the door to antibiotic project in the emergency department from July 2025 through February 2026.

Goal

Reduce the average time from arrival to first antibiotic for patients meeting sepsis criteria. The starting average was 68 minutes. The target is under 45 minutes.

Where we are

The monthly mean has fallen from 68 minutes to 51 minutes over eight months.

The share of cases treated within 60 minutes rose from 41 percent to 75 percent.

The median now sits at 49 minutes, close to the target line.

What changed

A standing order set lets the nurse start the workup before the physician has finished the first assessment.

Antibiotics were moved to a ready location near triage to cut travel time.

A brief huddle at shift change flags any patient already on the sepsis pathway.

Next steps

Hold the gains through the busy winter months and watch for any drift on night shifts.

Add a simple feedback note to the team each week showing the running average.

Bring the night team into the next review so the improvement is even across all shifts.

Thanks to the nursing leads and the pharmacy team, who carried most of the day to day work on this.