Paris crate  -  packing and shipping checklist

Eight pieces for Earth and Hand. Ship by Fri 2 Oct 2026. Sagawa Art Logistics, Kyoto.

Before Sagawa collect

Confirm the final eight after the May firing comes out. Do not pack a piece I am not sure of.

Photograph each piece, all sides, for the condition record and my own files. Riku has the gallery shots, these are the insurance ones.

Wrap each piece myself first, acid free tissue then bubble, I do not let the couriers wrap the ceramics.

Label each bundle with the ET tag from the selection list and the insured value.

Foam corners on the two tall vases. They are the fragile ones and the centre of the wall.

Crate and documents

Sagawa builds the export crate to their spec. Three internal compartments, A B and C per the selection list.

Commercial invoice for customs, marked as artist's original work, hand made ceramics, with the insured values in JPY and EUR.

Insurance certificate at total 798,000 JPY. Cost split with Galerie Terre per the agreement.

Keep a copy of everything. Email the tracking to Jean-Luc the day it ships.

Timeline

Mon 28 Sep: final pack at the studio.

Wed 30 Sep: Sagawa collect and crate.

Fri 2 Oct: crate ships. This date cannot move, customs needs the run up before the 17th.

Around 13 Oct: crate should reach the gallery. Jean-Luc unpacks and checks, sends me photos.

Thu 16 Oct: I arrive, see the pieces in place on the 17th.

If the firing is short and I only have one strong tall vase, tell Jean-Luc by early June so he can rework the hang. Better an honest seven than a weak eight.