## Seasonal Table
Seasonal Table - production tracker
Solo show, Shibui Gallery. Opening Sat 10 Oct 2026, 6pm. All work fired and finished by Mon 5 Oct.
Last updated 28 Feb 2026. 30 finished pieces needed for the show. I throw extra to cover loss, see note below.
Tag | Season | Form | Glaze | Qty thrown | Unit price | Status | Firing ref
ST-01 | Spring | Rice bowl | Mountain ash green | 4 | 4800 | Fired | F-26-01 / F-26-02 / F-26-03
ST-02 | Spring | Tea cup | Nuka white | 4 | 3800 | Fired | F-26-01 / F-26-02 / F-26-03
ST-03 | Spring | Small plate | Mountain ash green | 3 | 5200 | Fired | F-26-01 / F-26-02 / F-26-03
ST-04 | Spring | Serving bowl | Ash celadon | 1 | 14000 | Fired | F-26-01 / F-26-02 / F-26-03
ST-05 | Summer | Tumbler | Clear over iron | 4 | 3600 | Fired | F-26-01 / F-26-02 / F-26-03
ST-06 | Summer | Side plate | Nuka white | 3 | 4800 | Fired | F-26-01 / F-26-02 / F-26-03
ST-07 | Summer | Pouring jug | Ash celadon | 1 | 12500 | Fired | F-26-01 / F-26-02 / F-26-03
ST-08 | Summer | Dipping dish | Tenmoku | 4 | 2600 | Fired | F-26-01 / F-26-02 / F-26-03
ST-09 | Autumn | Noodle bowl | Tenmoku | 3 | 5400 | Glazed, awaiting firing | next gas firing, late Mar
ST-10 | Autumn | Tea bowl | Kaki iron red | 2 | 6800 | Glazed, awaiting firing | next gas firing, late Mar
ST-11 | Autumn | Dinner plate | Mountain ash green | 3 | 6200 | Bisque | May anagama F-26-05
ST-12 | Autumn | Vase | Wood ash natural | 1 | 18000 | Bisque | May anagama F-26-05
ST-13 | Winter | Soup bowl | Tenmoku | 4 | 5200 | Fired | F-26-01 / F-26-02 / F-26-03
ST-14 | Winter | Sake cup set | Nuka white | 4 | 2800 | Greenware | to throw / May anagama
ST-15 | Winter | Large platter | Ash celadon | 1 | 22000 | Greenware | to throw / May anagama
|  | Finished pieces needed: |  | 30
|  | Line items still not fired: |  | 6
|  | Potential retail value (all thrown): |  | 236100
Note: I throw roughly 40 percent over the count. Spring and summer sets are done. The autumn noodle bowls and the winter sake set are the worry. Talk to Mika about a slot in the late March gas firing so the autumn set is not riding on the May anagama alone.