## Slide 1
HARBORVIEW REGIONAL, EMERGENCY DEPARTMENT
Chest-Pain Triage Protocol
Rollout plan and stage gates toward the Q1 2027 go-live
Nate Wright

## Slide 2
01
Why this protocol
The problem we are closing
Front-door assessment of adult chest pain varies between shifts at a 320-bed Level II trauma centre. The aim is one repeatable pathway so a 12-lead EKG and risk score happen inside a defined window every time.
Ownership
Owner: Nate Wright, PA-C. Sponsor: Dr. Karen Ashworth, ED department head. Clinical input: Dr. Phil Engstrom. Nursing in-service led with Becca Solis, the charge nurse on the usual shifts.
What good looks like
Shorter door-to-decision time, less variation between the day and night teams, and a clean 90-day audit baseline that the two precepting students can help present at the cohort review.

## Slide 3
02
The decision tree
Identify at arrival
Triage nurse flags chest pain or an anginal equivalent on arrival. Immediate vitals, then a 12-lead EKG ordered to the agreed time-to-EKG target. The exact threshold is being finalised with Dr. Engstrom and is not quoted from any older draft.
Read and route
Provider reads the EKG. A STEMI activates the cath-lab line directly. A non-STEMI moves to a structured risk score, a troponin draw, and disposition guidance written into the order set.
Safe discharge
A low-risk discharge carries a documented safety-net note and a follow-up plan, so nothing leaves the department without a written next step.

## Slide 4
03
Stage gates to go-live
October to November 2026
Finalise the triage decision tree and lock the time-to-EKG target. Circulate the final draft for attending sign-off, then run the nursing in-service sessions and a dry-run on three simulated arrivals.
December 2026
IT build of the order set, the smartphrase, and the audit dashboard. Content changes freeze by mid-December so the build is stable before the soft launch.
January to February 2027
Soft launch on day shift only with daily huddle debriefs for two weeks, then full rollout across all shifts and the start of the 90-day audit.

## Slide 5
04
Open items and discipline
Confirm the number first
Lock the final time-to-EKG threshold with Dr. Engstrom before any deck is printed. The clinical numbers carry real weight, so precision matters more than speed and no figure ships from an older draft.
Keep the tools in step
The milestone row in the project tracker and the task board must stay in step with the working file. When a value changes, update the live picture and flag it next time it is relevant rather than overwriting quietly.
Teaching scaffold
Decide whether the precepting students present the audit baseline at the December cohort review. The protocol doubles as the EKG-reading teaching frame for the visiting rotation.