## Slide 1
GREATER HOPE BAPTIST CHURCH
75th Anniversary Celebration Planning
October 17, 2026 - 16400 Pembroke Avenue, Detroit, MI 48235
Lead Coordinator: Deacon Shawn Dawson | Senior Pastor: James Caldwell
Planning subcommittee formed February 15, 2026

## Slide 2
Event Overview
What we are celebrating and what we want this day to be
Greater Hope Baptist Church 75th Anniversary | Planning Document | February 2026
PURPOSE: To mark seventy-five years of Greater Hope with a celebration that honors the founders, welcomes the wider community, and reflects the spirit of service the church has carried since its first Sunday.
Date and Time
Sunday, October 17, 2026 After morning service - approximately 1:00 PM
Location
Greater Hope Baptist Church 16400 Pembroke Avenue, Detroit, MI 48235
Lead Coordinator
Deacon Shawn Dawson Subcommittee formed Feb 15, 2026
Church Contact
Linda Marsh, Church Secretary Pastor James Caldwell presiding
The goal: a full house and a warm welcome. Every member who helped build this church deserves to be seen on this day.

## Slide 3
75 Years of Greater Hope
A brief timeline of our history and milestones
Greater Hope Baptist Church 75th Anniversary | Planning Document | February 2026
1951
Founding
Greater Hope Baptist Church established in northwest Detroit by a small congregation of twelve founding families.
1960s
Community anchor
The church becomes a gathering point during the civil rights era. Pastor-led voter registration drives and neighborhood outreach.
1970s-80s
Growth and building
Congregation grows. The Pembroke Avenue building is expanded to accommodate the growing membership.
1990s
Deacon board established
Deacon structure formalized. Community outreach programs expanded including the food drive and sick visitation ministry.
2004-now
Pastor James Caldwell
Twenty years of pastoral leadership. Greater Hope grows into a multi-generational congregation serving northwest Detroit.
Oct 17, 2026
75th Anniversary Celebration
The milestone we are planning today. A day of worship, remembrance, and thanksgiving.

## Slide 4
Proposed Program
Draft order of service for the 75th Anniversary
Greater Hope Baptist Church 75th Anniversary | Planning Document | February 2026
Time
Event
Lead / Notes
1:00 PM
Welcome and Call to Worship
Pastor James Caldwell
1:15 PM
Historical reflection
Founding families and long-tenured members
1:45 PM
Musical tribute
Choir and special guests
2:15 PM
Community recognition
Deacon board and ministry leaders recognized
2:45 PM
Special anniversary message
Pastor Caldwell
3:15 PM
Closing prayer and fellowship
Deacon Dawson - lead
3:30 PM
Reception and memorial display
Open to all - founding photos and church archive

## Slide 5
Budget and Building Fund Status
Current fund position and anticipated anniversary costs
Greater Hope Baptist Church 75th Anniversary | Planning Document | February 2026
Building Fund - February 2026
Opening balance (Jan 1, 2026)
$18,450.00
Jan 11 - Special offering
+$2,240.00
Jan 18 - Designated gifts
+$875.00
Feb 1 - Boiler inspection
-$320.00
Feb 8 - Special offering
+$1,980.00
Feb 15 - 75th anniversary gifts
+$1,100.00
Feb 22 - Parking lot seal
-$880.00
CURRENT BALANCE
$23,445.00
Anniversary Budget (Estimated)
Catering and reception food
$1,800 - $2,400
Anniversary program booklets
$350 - $500
Flowers and decorations
$400 - $600
Sound and audiovisual
$300 - $500
Photography
$400 - $600
Guest minister honorarium
$200 - $400
Choir accompanist
$150 - $250
Memorial display and archive
$200 - $350
TOTAL ESTIMATED RANGE
$3,800 - $5,600
Any commitment at or above the board approval threshold requires full deacon board review before signing. Budget to be confirmed at the next board meeting.

## Slide 6
Volunteer and Committee Roles
Who is responsible for what on the day and in the weeks before
Greater Hope Baptist Church 75th Anniversary | Planning Document | February 2026
Role
Assigned To
Responsibilities
Lead Coordinator
Deacon Shawn Dawson
Overall planning, budget oversight, final program approval, day-of coordination
Church Secretary
Linda Marsh
Communications, RSVPs, bulletin insert, member notifications
Facilities
To be assigned
Room setup, parking, AV check, reception tables
Catering
To be assigned
Food coordination and serving team
Photography
To be assigned
Event photography, archive display
Hospitality
To be assigned
Welcome table, visitor management, elder assistance
Choir
Church music director
Musical selections and rehearsal coordination

## Slide 7
Pre-Event Checklist
Tasks to complete before October 17, 2026
Greater Hope Baptist Church 75th Anniversary | Planning Document | February 2026
Priority
Task
Timing
Board approval
Confirm budget at next deacon board meeting
Priority
Catering
Select vendor and sign contract - minimum 6 weeks out
Priority
Program booklet
Design, review, and print - 3 weeks before event
Priority
Guest invitations
Mail to founding families and long-tenured members
4 weeks out
Sound check
Schedule AV team walkthrough day before event
1 week out
Archive display
Gather founding photos and historic church documents
4 weeks out
Bulletin announcement
Pastor Caldwell to announce from pulpit - 4 Sundays before
Ongoing
Final headcount
Lock attendance count 2 weeks before for catering
2 weeks out
Thank you letters
Prepare for all volunteers and donors post-event
Post-event

## Slide 8
Seventy-Five Years of Greater Hope
The goal is a full house and a warm welcome.
Every member who helped build this church deserves to be seen on October 17, 2026.
Greater Hope Baptist Church - 16400 Pembroke Avenue, Detroit, MI 48235 - (313) 555-6650
Lead Coordinator: Deacon Shawn Dawson - (313) 555-3920 | Secretary: Linda Marsh - (313) 555-1144