## Slide 1
CHT Certification Roadmap
From 2,800 logged hours to the January 9, 2027 exam
Meghan Yuki Douglas, OTR/L | Pacific Rehabilitation Associates, Honolulu

## Slide 2
Agenda
1. Where the hour count stands today
2. The supervised and solo split
3. Domain readiness before the practice exam
4. Study cadence through the fall
5. Timeline to January 9, 2027

## Slide 3
Hour count snapshot
Metric | Value
Hours logged | 2,800
Hours required | 4,000
Hours remaining | 1,200
Weekly hand therapy pace | 22 hours
Practice exam | November 7, 2026
70 percent of the
practice requirement
is complete.

## Slide 4
Hours logged by month
Chart: 
| Sep | Oct | Nov | Dec | Jan
Cumulative hours | 2710 | 2780 | 2855 | 2930 | 3000

## Slide 5
Study cadence
Thursday evenings 6:00 to 8:00 PM, online hand therapy review course
  Module 7 complete, flexor tendon focus
Weekly 1:1 with Dr. Park, Thursdays 4:00 PM, 30 minutes
  Cosign solo sessions so they count toward the log
Drill weakest domains after the November 7 practice exam

## Slide 6
The math is the math
Steady pace, log every hour, exam day January 9, 2027.
Prepared by Meghan Douglas, OTR/L