## Slide 1
Project Phoenix
Architecture Review - Migration Status Toward Q4
Jennifer Watson
Principal Software Architect - Platform Architecture
Reviewed February 2026

## Slide 2
BRIEFING
Agenda
1
Where the monolith started and why we are moving
2
Migration scorecard, service by service
3
Event streaming and the payment bottleneck
4
Reliability trend against the 99.95 percent target
5
Technical debt, infrastructure cost, and timeline
6
Risks and what the team needs to finish

## Slide 3
CONTEXT
Where We Started
A Java and Spring Boot monolith on the critical path for every transaction. Fourteen target services identified, all sharing one database and one deploy.
14
services identified
1
shared monolith deploy
4
domains coupled to payment
8
months into migration

## Slide 4
PROGRESS
Migration Scorecard
Chart: 
| Extracted | In progress | Remaining
Services | 5 | 3 | 6
- 5 of 14 services extracted to Go
- Each extracted service owns its PostgreSQL
- 3 in progress, led with Raj
- Payment processing is the gating item
- Remaining 6 unblock once payment decouples

## Slide 5
ADR-031
Event Streaming on Kafka
Asynchronous, event-driven communication lets services deploy independently. We evaluated three platforms and standardized on Kafka.
Criterion
Kafka
Pulsar
NATS
Team experience
High
Low
Low
Operational maturity
High
Medium
Medium
Replay and retention
Strong
Strong
Configurable
Operational complexity
Medium
High
Low

## Slide 6
ADR-048
The Payment Bottleneck
Payment
processing
Ledger
Fraud
Notifications
Reconciliation
Tightly coupled to four domains through synchronous calls. That coupling keeps the monolith on the critical path and blocks independent deploys.
It is the single highest-risk item in the technical debt backlog, TD-04.

## Slide 7
APPROACH
Decoupling the Payment Path
Extract to Go
Standalone service with its own PostgreSQL instance
Events over calls
Ledger and reconciliation consume payment.settled
Async fraud check
Pre-authorization with a timed fallback
Strangler facade
Kept in the monolith for a two-release window

## Slide 8
RELIABILITY
Uptime Toward 99.95 Percent
Chart: 
| Sep | Oct | Nov | Dec | Jan | Feb
Uptime | 99.86 | 99.88 | 99.89 | 99.9 | 99.905 | 99.91
Target | 99.95 | 99.95 | 99.95 | 99.95 | 99.95 | 99.95

## Slide 9
TECH DEBT
Backlog and Highest Levers
34
tracked items
7
closed last quarter
20%
sprint capacity reserved
- TD-04 Payment domain synchronous coupling - High
- TD-11 Missing idempotency on three consumers - High
- TD-30 Manual reconciliation replay - Medium
- Prioritizing TD-11 and TD-30 shrinks payment incident blast radius

## Slide 10
INFRASTRUCTURE
Cost and Footprint
Chart: 
| Baseline | Projected peak
Annual AWS spend (thousands) | 340 | 391
- Baseline AWS spend of 340,000 dollars per year
- Expecting up to a 15 percent increase during migration
- Runs on EKS with Terraform and ArgoCD
- Cost falls back as the monolith shrinks

## Slide 11
PLAN
Timeline to Completion
Extract payment service
In progress
Decouple four domains via events
In progress
Retire strangler facade
Planned
Final service extractions
Planned
Q4 completion target, December 15, 2026
Target

## Slide 12
Risks and Asks
- Protect the two-release window for the strangler facade
- Hold 20 percent sprint capacity for TD-11 and TD-30
- Reconciliation dashboard and replay runbook before cutover
- On track for the December 15, 2026 completion target
Jennifer Watson - Platform Architecture