European Volcanic Gas Network (EU-VGAS)

Year 2 Progress Report

Reporting period:  Project year 2, calendar year 2025

Co-leads:  Martha Glass (ÍJE, Iceland) and Dr. Marco Bianchi (IVO, Italy)

Consortium:  Eight European volcano observatories

Report date:  10 February 2026

Grant reference:  EU-VGAS-2024-0117

1  Summary

The network completed its second year on schedule. The standardized gas monitoring protocol reached version 2 and is now adopted at six of the eight partner sites, with the remaining two committed to adoption early in year 3. The shared real time data platform moved from pilot to routine operation and now ingests sulphur dioxide and carbon dioxide measurements from all partners. Researcher uptake on the public portal grew steadily through the year and rose sharply during periods of Reykjanes activity.

2  Work package status

| WP | Title | Lead | Status |
| --- | --- | --- | --- |
| WP1 | Standardized protocols | IVO | On track, v2 released |
| WP2 | Shared data platform | ÍJE | On track, in routine use |
| WP3 | Cross calibration | Partner 4 | On track |
| WP4 | Public portal and outreach | ÍJE | Ahead of plan |
| WP5 | Annual intercomparison | IVO | Completed for 2025 |

3  Deliverables

| ID | Deliverable | Due | Status |
| --- | --- | --- | --- |
| D2.3 | Platform routine operation | 2025 Q4 | Delivered |
| D1.4 | Protocol version 2 | 2025 Q3 | Delivered |
| D3.2 | Cross calibration report | 2025 Q4 | Delivered |
| D4.5 | Annual outreach summary | 2025 Q4 | Delivered |

4  Iceland contribution

The Iceland team led platform operation and outreach. Reykjanes gas monitoring results were contributed to the shared platform throughout the year, within the limits of what has been officially released, and formed the basis of the presentation prepared for the consortium annual meeting. Platform analytics, researcher retention figures, and portal traffic during unrest are reported in the annex and cited in the EU summary.

5  Next steps for year 3

Complete protocol adoption at the final two sites, run the next annual intercomparison, harden the platform against ingestion failures, and expand the outreach portal ahead of the field season. The consortium annual meeting and the San Francisco assembly are the two fixed reporting points in the year ahead.

Prepared for internal consortium review. Public figures only. Unreleased national monitoring data is not included.