Highland Gas Survey, July 2025

Field Safety and Logistics Plan

Campaign lead:  Martha Glass, ÍJE

Field team:  Lilja Einarsdóttir (PhD), two field assistants, Dr. Sarah Jennings (visiting, PNVO)

Helicopter support:  Halldór Bjarnason, Hekla Air Services

Dates:  14 to 28 July 2025

Sites:  Katla caldera rim, Bárðarbunga, Askja

Plan date:  2 June 2025

1  Objectives

Collect baseline gas measurements at the three target systems using DOAS, MultiGAS, and drone mounted sensors. Priority is the Katla caldera rim baseline, which feeds directly into the readiness assessment. Secondary objectives are repeat measurements at Bárðarbunga and a first survey at Askja for the season.

2  Weather and helicopter windows

All flying is at the discretion of the pilot. Halldór has final say on every lift, and a no from him is final and never questioned. Highland weather windows are short and shift fast, so the schedule below is a target, not a promise. We carry two spare field days for weather. Forecasts are checked the evening before and again at first light.

| Day | Site | Primary task | Weather backup |
| --- | --- | --- | --- |
| 1 to 4 | Katla rim | Caldera rim baseline survey | Move to Day 5 slot |
| 5 to 7 | Bárðarbunga | Repeat MultiGAS and DOAS | Drone only if wind allows |
| 8 to 11 | Askja | First season survey | Ground sampling fallback |
| 12 to 14 | Reserve | Weather and instrument catch up | Demob |

3  Communications

Primary field communication is the Garmin inReach satellite link for position and check in, with a fixed morning and evening schedule. Telegram is used for team coordination when within coverage. A missed evening check in triggers the escalation procedure after a two hour grace period. Base contact holds the full passenger and payload manifest for every lift.

4  Safety and emergency procedure

Every team member carries personal protective equipment for gas exposure, including a gas mask rated for sulphur species and a personal H2S alarm. No one approaches a fumarole alone. Crevasse protocol applies on all glaciated ground. In an emergency, contact base by inReach, then Hekla Air Services, then ICE-SAR through the 112 system. Medical kit and evacuation roles are assigned at the daily briefing.

5  Provisioning and gear

Food and fuel for sixteen days, two days beyond plan. Instrument spares for the DOAS and MultiGAS units, spare drone batteries, and a portable weather station. Dietary requirements from the pre campaign forms are accommodated. Gear list and load plan are tracked separately for each helicopter lift.

Field plan only. Subject to change with weather and ground conditions. Pilot judgement overrides the schedule at all times.