## Slide 1
VOICES
UNHEARD
Community Story Collection
A first person storytelling campaign for autumn 2026, building toward the November gala.
Prepared by Sarah Patterson, Social Media Coordinator

## Slide 2
The objective
Collect and amplify first person stories from the communities we serve.
The series runs alongside our ongoing voter education content and feeds the gala fundraising push.
Tone is warm, direct, and plain. No performative optimism. The people we serve tell their own stories, in their own words.
What success looks like
Reach beyond our usual audience
Stories that donors remember at the gala
A library we can reuse all year

## Slide 3
Audience and channels
Photo Platform
Stories and carousels, the core feed
Short Video Platform
Behind the scenes and story clips
Social Network
Longer captions, event tie ins
Professional Network
Partner and funder facing posts
Microblog
Live quote threads on launch and gala nights

## Slide 4
Content pillars
The Story
A person, a moment, in their words
The Why
How the work changed the day to day
The Call
A clear, kind way to help

## Slide 5
Timeline
Oct 6 to Oct 15, 2026
Teasers and a call for stories
Oct 16, 2026
Soft launch, hero post across all channels
Oct 20 to Nov 7, 2026
One feature story per week
Nov 10 to Nov 14, 2026
Gala tie in and live coverage

## Slide 6
Engagement goals by phase
Chart: 
| Teaser | Soft launch | Weekly features | Gala tie in
Projected engagements | 1800 | 5200 | 3600 | 6400

## Slide 7
Stories first. Everything else follows.
Three story subjects confirmed by early October. Shot list with the programs team. All day monitoring on launch.