## Slide 1
Wedding Planning Status Review
Ryan and Emma | October 17, 2026 | Greystone Banquet Hall
Where the plan stands and what is left before the day
Prepared for the Wednesday planning night

## Slide 2
Where we are
110
Guest target
56
Confirmed so far
$41,200
Total budget
9
Vendors booked or paid
Highlights this cycle
• Catering, venue, florals, cake, photography, and music are all booked with deposits paid.
• Suit and rings are paid in full. Stationery is printed and ready.
• Final guest count is due to the caterer by October 13, 2026.

## Slide 3
Where the budget goes
Chart: 
| Catering | Venue | Photography | Florals | Music | Everything else
Budget | 10450 | 9200 | 4200 | 3400 | 1800 | 12150
The big three
• Catering at 95 dollars a head for 110 guests is the largest single line.
• Venue and photography together carry about a third of the plan.
• A contingency of 5,350 dollars sits inside everything else, held in reserve.

## Slide 4
Vendor status
Vendor | Estimate | Deposit | Balance | Status
Cedar Table Catering | $10,450 | $2,500 | $7,950 | Booked
Greystone Banquet Hall | $9,200 | $3,000 | $6,200 | Booked
Northline Photography | $4,200 | $1,400 | $2,800 | Booked
Bloom and Petal Florals | $3,400 | $1,000 | $2,400 | Booked
Motor City Sound, music | $1,800 | $600 | $1,200 | Booked
Saffron Bakehouse Cake | $950 | $300 | $650 | Booked

## Slide 5
Next steps before the day
1
Send the day of timeline to the wedding party group and confirm arrival times.
2
Final venue walkthrough on October 3, 2026 with Emma, Linda, and Diane.
3
Lock the final guest number with the caterer by October 13, 2026.
4
Pick up and press the suit the week of the wedding.
5
Confirm the antipasto course headcount and the Italian wine toast.