## Phase4
North Frisian Medieval Wreck Survey, Phase 4 logistics
Base Husum, season from 01.06.2027, DFG GR 4471/3
Work package | Detail | Owner | Start | Cost EUR | Status
Permits | Site access and dive permits, Nordfriesland | G. Gross | 2026-11-01 | 0 | to apply
Vessel charter | Survey vessel, 6 weeks | N. Johansen | 2027-05-15 | 18600 | quote held
Accommodation | Field house Husum, team of 6 | G. Gross | 2027-05-20 | 7200 | option
Dive operations | Air, gas, safety cover | N. Johansen | 2027-06-01 | 5400 | planned
Conservation | Wet storage and transport to museum | F. Moe | 2027-06-01 | 4100 | planned
Frisian consultation | Aurich meetings and travel | A. Reimer | 2026-12-01 | 1500 | agreed
Equipment | Multibeam hire and spares | G. Gross | 2027-04-01 | 6300 | to order
Total |  |  |  | 43100