# Monograph working notes

Working title: "Hanseatic Routes Beneath the German Bight"

Author: Gloria Gross. Draft target: 31.03.2027. Status updated 28.01.2026.

# Chapter plan

| No | Chapter | Words | Status |
| --- | --- | --- | --- |
| 1 | The German Bight as a maritime landscape | 8200 | drafted |
| 2 | Hanseatic routes and cargo evidence | 6100 | drafted |
| 3 | Survey methods and sonar at NF-7 | 4400 | in progress |
| 4 | The NF-7 vessel, hull and finds | 2600 | outline |
| 5 | Frisian knowledge and place names | 1200 | outline, with A. Reimer |
| 6 | Climate risk to submerged sites | 900 | outline |
| 7 | Conclusions | 0 | not started |

# Notes to self

Chapter 3 stalls because the find catalogue is not yet final. Treat this as evidence care, not avoidance. Next concrete step: close the NF7 find register with Frida, then write the methods section in the Monday writing block.

Total drafted so far about 22400 words. Do not promise chapter 4 before the conservation report is back.