North Frisian Medieval Wreck Survey

# Dive team planning, minutes

Date: 27.08.2025, Wednesday. Present: G. Gross (PI), N. Johansen (dive lead), A. Bergmann, L. Bruhn, T. Falk.

1. Season close. NF-7 detail excavation to finish 29.08.2025. Two dives remain, weather permitting. Go or no go stays with the field lead.

2. Finds. NF7-014 plank lifted and in wet storage. Transport to the museum coordinated with F. Moe. Standort data stays restricted.

3. Safety. Visibility dropped below two metres on 18.08, dive cancelled as per protocol. Confirm O2 kit checked before final dives.

4. Target T08. Possible adjacent wreck flagged on sonar, north of the main site. Not for this season. Carry into the Phase 4 plan for 2027.

5. Next steps. Schlussbericht and Phase 4 application due 05.11.2026. Next planning meeting every other Wednesday through the winter.