## Slide 1
North Sea Coastal Heritage Mapping
Year 3 Progress Report
North Sea Coastal Heritage Annual Consortium Meeting
Hamburg Maritime Museum | 12 November 2025
Co-PI: Prof. Dr. Gloria Gross, Nordmeer Maritime University
Co-PI: Dr. Frida Moe, Hamburg Maritime Museum
HMM-CHM-22 | Year 3 of 4 | Reporting period: January - October 2025

## Slide 2
Programme Status - Year 3
HMM-CHM-22 | Schleswig-Holstein Coastal Survey | 2022-2026
Seabed coverage
✓ Complete
74% of target area completed. Final 26% planned for summer 2026. Coverage map updated October 2025.
Feature register
✓ Complete
187 candidate features logged. 42 diver-inspected. 28 confirmed anthropogenic, 9 high-confidence medieval.
Frisian consultation
✓ Complete
4 community meetings held in 2025. A. Reimer confirmed for Year 4 advisory role. Protocol document updated.
Year 3 deliverables
✓ Complete
Year 3 progress report delivered. Feature catalogue updated. GIS data package transferred to museum.
Consortium outputs
In progress
1 conference paper presented (Hamburg Archaeology Days, October 2025). Journal submission in preparation.

## Slide 3
Feature Register - Year 3 Summary
187 candidate features | 42 diver-inspected | Distribution across 6 survey zones
187
Total features in register
42
Diver inspected
28
Confirmed anthropogenic
9
High-confidence medieval
5
Recommended for priority documentation
Zone breakdown:
Zone
Area (km2)
Coverage
Features logged
Inspected
Confirmed
North Frisian Outer
3.8
100%
42
18
12
Pellworm Channel
2.1
100%
31
10
7
Eiderstedt Coast
4.5
85%
38
6
4
Fohr-Amrum Gap
2.9
68%
29
5
3
Sylt Southern Approach
3.2
55%
27
3
2
Inner Wattenmeer (partial)
6.4
44%
20
0
0

## Slide 4
Year 4 Plan and Final Programme Deliverables
HMM-CHM-22 concludes December 2026 | All deliverables on track
Q1 2026
Complete survey coverage
NMU Field Team
Final MBES survey lines in Zones 5 and 6. Close coverage gap in Sylt Southern Approach.
Q2 2026
Diver inspection programme
G. Gross / N. Johansen
Inspect 20 high-priority features from Year 4 survey. Complete outstanding Year 3 inspections.
Q3 2026
Final feature catalogue
NMU / HMM Joint
Integrate all four years of survey data. Produce final GeoPackage for museum archive.
Q4 2026
Programme final report
G. Gross / F. Moe
Full report to heritage authority and DFG. Exhibition planning brief for museum. Frisian consultation close report.
Q4 2026
Journal publication
G. Gross / F. Moe / J. Whitfield
Submit joint paper on methodology and results to International Journal of Nautical Archaeology.

## Slide 5
Thank you
Questions and consortium discussion
Prof. Dr. Gloria Gross | g.gross@nordmeer-maritime.de
Dr. Frida Moe | f.moe@hamburgmuseum.de
Nordmeer Maritime University | Am Sandtorkai 48 | 20457 Hamburg
Hamburg Maritime Museum | HMM-CHM-22