## Slide 1
Downtown Bangor Commercial Rewiring
Phase Status Report and 30-Day Outlook
Project Lead: Teresa Gutierrez, Journeyman Electrician
Foreman: Steve Gilmore
Penobscot Electrical Contractors, 144 Perry Road, Bangor ME
Reporting period: November 5, 2026

## Slide 2
Project Scope
Three floors, full panel and branch-circuit replacement
• Whole-building rewire of a three-story downtown office building
• Replace branch circuits, distribution panels A, B, and C
• New lighting controls and occupancy sensors throughout
• Modern device counts to current NEC requirements
• Coordinated cutovers after hours to keep tenants live
• As-built drawings and inspector sign-off at closeout
Key Facts
Project start
October 14, 2026
Closeout target
January 29, 2027
Lead electrician
Teresa Gutierrez
Foreman
Steve Gilmore
Crew size on site
4 to 6
Working hours
7:00 AM to 3:30 PM, cutovers after hours
Permit number
BGR-COM-2026-1407
Penobscot Electrical Contractors
Slide 2 of 8

## Slide 3
Phase Timeline
Demo, rough-in, cutover, trim, and closeout
Phase | Area | Task | Target | Status
Phase 1 | Floor 1 East | Demo existing branch circuits | 11/06/2026 | Complete
Phase 1 | Floor 1 East | Pull new MC cable home runs | 11/20/2026 | In progress
Phase 1 | Main Room MDP | Panel A cutover, after hours | 11/25/2026 | Scheduled
Phase 2 | Floor 2 West | Rough in receptacles and switches | 12/11/2026 | Scheduled
Phase 2 | Floor 2 West | Panel B cutover, after hours | 12/18/2026 | Scheduled
Phase 3 | Floor 3 | Lighting controls and occupancy sensors | 01/08/2027 | Scheduled
Phase 3 | Floor 3 | Final trim, devices and labeling | 01/22/2027 | Scheduled
Closeout | Whole building | Inspection and as-built markups | 01/29/2027 | Scheduled
Lead: Teresa Gutierrez
Slide 3 of 8

## Slide 4
Crew Hours by Week
Week of November 2 through end of phase 1
Chart: 
| Wk 11/02 | Wk 11/09 | Wk 11/16 | Wk 11/23 | Wk 11/30
Teresa | 32 | 34 | 36 | 30 | 34
Danny | 32 | 32 | 36 | 28 | 32
Apprentice A | 30 | 32 | 34 | 28 | 32
Apprentice B | 24 | 28 | 30 | 24 | 28
Notes
• Voluntary overtime budgeted at time-and-a-half
• Cutover weekends shift one crew member to Saturday
• Apprentices roll off after Phase 1 trim
• Danny covers floor 2 rough-in while Teresa runs Panel A cutover
Penobscot Electrical Contractors
Slide 4 of 8

## Slide 5
Safety and Compliance
Arc flash, lockout-tagout, and PPE posture
0
Recordable incidents this project
4
Crew, all OSHA 30 current
12
LOTO procedures executed
100%
PPE compliance audits
Job Hazard Analysis highlights
• Arc flash boundary established at Panel A and Panel B, category 2 PPE on cutover nights
• Hot work permit on file for the MDP relocation; fire watch identified
• Aerial lift inspections logged daily; both operators current per Cert 04/22/2025
• Daily safety stand-up at 7:00 AM with the GC and the trades on site that day
OSHA 30 current for all crew
Slide 5 of 8

## Slide 6
Materials Spend to Date
Phase 1 and ordered for Phase 2
Chart: 
| MC cable | Panels and breakers | Devices and trim | Lighting controls | Conduit and supports | Consumables
USD | 8420 | 6150 | 2980 | 4310 | 1860 | 1280
Category | USD
MC cable | $8,420
Panels and breakers | $6,150
Devices and trim | $2,980
Lighting controls | $4,310
Conduit and supports | $1,860
Consumables | $1,280
Total to date | $25,000
Procurement: Aubuchon and Granite City Electric
Slide 6 of 8

## Slide 7
Risk Register
Top risks tracked weekly
Risk | Likelihood | Impact | Owner | Mitigation
MDP relocation slips into Thanksgiving week | Medium | High | Teresa | Confirm GC sign-off by 11/18, pre-stage panel A on 11/22
Lighting controls back-order | Medium | Medium | Steve | Place Phase 3 order by 11/30, alt vendor identified
Tenant after-hours access friction | Low | Medium | GC | Standing badge list; security walkthrough each cutover
Weather delay on rooftop conduit run | Low | Low | Crew | Indoor priority list available for cold days
Inspector availability in late January | Medium | High | Steve | Pre-book inspection slot for 01/28 by 12/15
Owner labels reflect on-site responsibility
Slide 7 of 8

## Slide 8
Next 30 Days
Through end of phase 1 and into rough-in
• Wk 11/09: finish floor 1 east MC home runs, label terminations
• Wk 11/16: panel A pre-stage, after-hours walk on 11/20
• Wk 11/23: panel A cutover overnight 11/24 into 11/25
• Wk 11/30: start floor 2 west rough-in, devices and switches
Asks of the office
• Confirm overtime budget for the 11/24 cutover
• Approve Phase 3 lighting controls PO by 11/30
• Schedule a second arc flash refresher for Q1 2027
• Block off 01/28 for inspector walk-through
Questions: tgutierrez@penobscotelectrical.com
Slide 8 of 8