## Schedule
Downtown rewiring, Penobscot Electrical Contractors
Lead: Teresa Gutierrez Foreman: Steve Gilmore
General contractor posts the punch list, update card status after each cutover
Phase | Area | Task | Status | Target
Phase 1 | Floor 1 East | Demo existing branch circuits | Complete | 11/06/2026
Phase 1 | Floor 1 East | Pull new MC cable home runs | In progress | 11/20/2026
Phase 1 | Main Room MDP | Panel A cutover, after hours | Scheduled | 11/25/2026
Phase 2 | Floor 2 West | Rough in receptacles and switches | Scheduled | 12/11/2026
Phase 2 | Floor 2 West | Panel B cutover, after hours | Scheduled | 12/18/2026
Phase 3 | Floor 3 | Lighting controls and occupancy sensors | Scheduled | 01/08/2027
Phase 3 | Floor 3 | Final trim, devices and labeling | Scheduled | 01/22/2027
Closeout | Whole building | Inspection and as-built markups | Scheduled | 01/29/2027