## Backlog
Lantern Keeper, Task List
Solo build ¦ Updated February 15, 2026 ¦ Sunday afternoons
ID | Task | Area | Priority | Estimate (hrs) | Status | Target | Notes
LK-01 | Carry mechanic, light radius and growth waking | Mechanics | High | 6 | Done | Dec 2025 | Feels right, keep the falloff soft
LK-02 | Place mechanic, lantern stand holds platform | Mechanics | High | 5 | Done | Dec 2025 | Needed a clear visual for held state
LK-03 | Throw mechanic, short arc and recall | Mechanics | High | 7 | Done | Jan 2026 | Recall timing tuned to 1.5s
LK-04 | Dim mechanic, pass light-sensitive creatures | Mechanics | Medium | 6 | In progress | Oct 2026 | Creature stir threshold needs work
LK-05 | Region 1 gray box, teach carry | Levels | High | 8 | Done | Jan 2026 | Six rooms, one idea each
LK-06 | Region 2 gray box, teach place | Levels | High | 8 | In progress | Oct 2026 | Two rooms blocked on LK-04
LK-07 | Region 3 gray box, teach throw | Levels | Medium | 8 | Backlog | Nov 2026
LK-08 | Region 4 gray box, teach dim | Levels | Medium | 8 | Backlog | Nov 2026 | Depends on LK-04 final
LK-09 | Region 5, braid all four verbs | Levels | Medium | 10 | Backlog | Dec 2026 | The quiet finale room
LK-10 | Ambient music pass, region 1 | Audio | Medium | 5 | In progress | Oct 2026 | Pads plus sparse piano
LK-11 | Sound design, waking wood and lamp hum | Audio | Low | 4 | Backlog | Nov 2026
LK-12 | Lantern light shader, soft grain | Art | Medium | 6 | Done | Jan 2026 | Looks great at night palette
LK-13 | Title screen art and logo | Art | Low | 4 | In progress | Oct 2026 | See concept sketch
LK-14 | Save and checkpoint system | Systems | High | 6 | Backlog | Oct 2026 | Quiet auto save on room enter
LK-15 | Options menu, remap and audio sliders | Systems | Low | 3 | Backlog | Dec 2026
LK-16 | Vertical slice build and playtest | Milestone | High | 8 | Backlog | Dec 2026 | Target: polished slice by year end