## Slide 1
HONEYCOMB BAKERY RVA, CARYTOWN
Holiday Gift-Box Program
2026 Season Plan, prepared by Aiden McCarthy

## Slide 2
WHERE WE LANDED
2025 result, 2026 target
73
boxes sold in 2025
$5,259
gross, 2025 program
90 to 100
box goal for 2026
110
stretch goal
Program runs October through early January. Pre-orders open mid-October. Production window December 1 to 23. Pickup at the bakery or shipping by UPS and USPS. In-store Open House the first Saturday of December.

## Slide 3
THE LINEUP
2026 boxes and pricing
SKU | Box | Price | Contents
HGB-S | Classic | $48 | Country Sourdough, Seeded Rye, 6 Almond Financiers, Spiced Brittle 4oz
HGB-M | Baker's | $72 | 2 Country Sourdough, Einkorn Batard, 8 pastries, Brittle, Honey 4oz
HGB-L | Full Honeycomb | $95 | 2 Sourdough, Rye, Einkorn, 12 pastries, Brittle, Honey 8oz, tote
HGB-GF | GF Gift Box | $68 | 2 GF Miche, 8 GF Financiers, 4 GF Muffins, Honey 4oz

## Slide 4
PRODUCTION
How the boxes get made
- Bread component: Kenji handles the Saturday bake, cooled overnight, slipped into bags Sunday morning
- Pastry component: Aiden preps financiers and muffins Tuesday and Wednesday during ship weeks
- Brittle made in one batch on the Tuesday of each ship week
- Honey add-on ordered from Shenandoah Valley Apiary, minimum 50 jars, order by November 1
- All production completed by December 22, no SKU shortages in 2025

## Slide 5
CALENDAR
Key 2026 deadlines
Date | Milestone
October 15, 2026 | Packaging order placed, Etsy and BigCommerce listings live
October 20, 2026 | Newsletter to subscriber list, pre-order announcement
November 1, 2026 | Instagram posts begin, three per week
December 5, 2026 | Holiday Open House, 9 AM to 2 PM, final pre-order deadline
December 20 to 23 | Pickup window and final shipping days
January 5, 2027 | Post-season recap and thank-you email

## Slide 6
BUDGET
Estimated 2026 economics
$6,480
revenue, 90 boxes at $72 avg
$3,203
total costs
$3,277
net estimated
Costs: ingredients and honey $1,540, packaging $680, shipping materials $190, marketing $145, Etsy and payment fees about $648. Margins hold as long as honey and flour costs stay near current levels.

## Slide 7
WHAT WE LEARNED
Carrying 2025 lessons into 2026
- Move more shipping to UPS Ground, USPS crushed two boxes last year
- GF Gift Box sold out first, add five more to the 2026 allocation
- Spiced brittle was the most mentioned item in reviews, keep the recipe exactly
- Close the Open House at 2 PM, customers arrived after the 2025 sellout
- List the honey add-on at launch, not in November, to capture early sales