HONEYCOMB BAKERY RVA

Holiday Gift-Box Program -- Planning Notes

Season: November through December 2026

Last updated: October 2026 (prep for launch)

Working doc -- not for distribution

---

OVERVIEW

The gift-box program runs October through early January. Pre-orders open mid-October. Production window is December 1 through December 23. Pickup at the bakery or Richmond-area shipping via UPS/USPS. In-store Holiday Open House first Saturday of December.

Last season (2025): 73 boxes sold. Revenue from gift-box program: approximately $5,259 gross.

Goal for 2026: 90 to 100 boxes. Stretch: 110.

---

SKUs FOR 2026

HGB-S     Classic Box (small)           $48    Country Sourdough x1, Seeded Rye x1, Almond Financiers x6, Spiced Almond Brittle 4oz

HGB-M     Baker's Box (medium)          $72    Country Sourdough x2, Einkorn Batard x1, Pastry selection x8, Spiced Brittle 4oz, Honeycomb Honey 4oz jar

HGB-L     Full Honeycomb Box (large)    $95    Country Sourdough x2, Seeded Rye x1, Einkorn Batard x1, Pastry selection x12, Spiced Brittle 6oz, Honey 8oz jar, Tote bag

HGB-GF    GF Gift Box                   $68    GF Miche x2, GF Almond Financiers x8, GF Lemon Olive Oil Muffins x4, Honey 4oz jar

HGB-ADD   Add-on: Honeycomb Honey 4oz   $12    Local wildflower honey, Shenandoah Valley Apiary

HGB-ADD2  Add-on: Spiced Brittle 4oz    $10    House-made with pumpkin seeds, almonds, cardamom, and sea salt

---

PRODUCTION NOTES

Bread component: Kenji handles Saturday bake. Breads for boxes go into the Saturday evening cool, slip into bags Sunday AM.

Pastry component: Aiden preps financiers and muffins Tuesday and Wednesday during gift-box weeks. Brittle made in one big batch on Tuesday of each ship week.

Honey add-on: Ordered from Shenandoah Valley Apiary. Minimum order 50 units (4oz jars). Order by November 1 for first ship window.

---

PACKAGING ORDER DEADLINE: October 15, 2026

Box: Kraft tuck-top boxes with Honeycomb Bakery stamp. Source: Packlane. Order 150 units minimum.

Tissue paper: Honeycomb yellow tissue, 20x30 sheets. Order 300 sheets.

Tote bag (HGB-L only): Natural canvas, Honeycomb stamp. Order 30 units.

Insert card: Printed card with product notes and message from Aiden. Print at Office Depot, 100 copies.

---

MARKETING TIMELINE

October 15, 2026    Etsy listings live, BigCommerce open

October 20, 2026    Mailchimp newsletter to subscriber list (pre-order announcement)

November 1, 2026    Instagram posts begin (3 per week through December)

December 5, 2026    Holiday Open House (9 AM to 2 PM)

December 5, 2026    Final pre-order deadline for December 20 pickup or ship

December 15, 2026   Reminder email to all pre-orders (pickup instructions)

December 20-23      Pickup window and final shipping days

January 5, 2027     Post-season recap and thank-you email

---

BUDGET (estimated)

Revenue (90 boxes, average $72): $6,480

Ingredients and honey add-ons: $1,540

Packaging: $680

Shipping materials and labels: $190

Marketing (Klaviyo upgrade, printing): $145

Etsy and payment fees (~10%): $648

NET ESTIMATED: $3,277

---

NOTES FROM 2025

12 boxes arrived damaged via USPS -- switch more volume to UPS Ground

HGB-GF sold out first -- add 5 more to 2026 allocation

Spiced brittle was the most-mentioned item in reviews -- keep recipe exactly as is

Open House sellout by 11:30 AM -- consider closing an hour later in 2026

Honey add-on added late (November 10) -- list it at launch in 2026