## Production
Holiday Cookie Box Production Plan
November and December 2026. Order cutoff December 18 for guaranteed pickup.
Box | Cookies | Target boxes | Total cookies | Price | Projected revenue
Small | 12 | 180 |  | 42
Medium | 24 | 240 |  | 58
Large | 40 | 90 |  | 74
Totals
Bake week | Focus | Boxes to finish
Week of Nov 30 | Doughs portioned and frozen, decorate test | 0
Week of Dec 7 | Drop and cut cookies, first 120 boxes | 120
Week of Dec 14 | Decorating push, 240 boxes | 240
Week of Dec 21 | Final boxes and pickups, 150 boxes | 150
Note: Christmas Eve the shop closes at 2:00 PM, that is the last pickup. Keep packaging stock ahead, last year we ran short on the medium tins.