## Slide 1
URISN Year 3 Renewal
Sustaining respiratory illness surveillance across Baltimore
Prepared for the Meridian Public Health Foundation
Grant MPH-2023-URB-0417 | Renewal request $141,667
Gerald Marie Roman, PhD, MPH, Principal Investigator | Submission due November 9, 2026

## Slide 2
Renewal aims
Aim 1
Continue prospective surveillance across all six sites with at least 80 percent retention.
Aim 2
Test whether change in housing quality between Year 1 and Year 3 tracks change in illness incidence.
Aim 3
Deliver a community synthesis report for residents, policymakers, and the Foundation.
Aim 4
Disseminate through two peer-reviewed papers and one national conference talk.

## Slide 3
Follow-up retention through Year 2
Chart: 
| Q1 24 | Q2 24 | Q3 24 | Q4 24 | Q1 25 | Q2 25
Retention (%) | 88 | 89.5 | 90.4 | 91 | 91.2 | 91.4

## Slide 4
Year 3 budget allocation
Chart: 
| Personnel | Field operations | Data and analysis | Community translation | Indirect
Budget | 78000 | 21000 | 15000 | 12000 | 15667
Total renewal request
$141,667
Personnel covers 50 percent PI effort, the biostatistician, and two research assistants. Indirect costs are held at the Foundation standard rate.

## Slide 5
Renewal period timeline
Oct to Dec 2026
Q4 site visits, housing re-assessment, Chicago talk
Jan to Mar 2027
Data cleaning, longitudinal dataset, Aim 2 analysis
Apr to Jun 2027
Submit Aim 2 manuscript, draft synthesis report
Jul to Sep 2027
Disseminate report, final Foundation progress report