## Slide 1
TURNER CONSTRUCTION
Harrison 24-Unit Residential Build Q4 2026 Progress Report
330 Bergen Ave · Harrison, NJ · Project Start: January 2026 · Projected Completion: December 2026
Prepared by: Lisa Reyes, Construction Foreman
Superintendent: Tony Rizzi | Director: Frank Delmonico
Report Date: October 1, 2026
▌ Units Framed 24 / 24 ▌ MEP Rough-In 21 / 24 ▌ Drywall 18 / 24 ▌ Concrete Pour Dec 9, 2026

## Slide 2
Project At A Glance
LOCATION
330 Bergen Ave Harrison, NJ
SCOPE
24-Unit Residential Build
CONTRACT VALUE
$9.27 Million
CREW SIZE
18 Workers (Current Phase)
SCHEDULE
Jan to Dec 2026 Dec 2026
STATUS
ON TRACK
Turner Construction · Newark Regional Office · Foreman: L. Reyes

## Slide 3
Milestone Tracker
Site Prep & Excavation
Jan to Feb 2026
✔ COMPLETE
Foundation & Footings
Feb 2026
✔ COMPLETE
Structural Framing
Early 2026
✔ COMPLETE
MEP Rough-In (all 24 units)
Complete
✔ COMPLETE
Structural Framing Inspection
Oct 1, 2026
✔ COMPLETE
Drywall & Interior Finishing
Through Nov 2026
⚙ IN PROGRESS
Final Concrete Pour
Dec 9, 2026
◷ SCHEDULED
Punch-List & Closeout
Dec 10 to 17, 2026
◷ SCHEDULED
Completion Walkthrough, Client
Dec 18, 2026
◷ SCHEDULED
■ Complete ■ In Progress ■ Scheduled

## Slide 4
Current Phase: Drywall & Interior Finishing
UNIT STATUS (as of Oct 1)
Units | Status | Target Complete
1 to 6 | Drywall Done, Paint In Progress | Oct 15
7 to 12 | Drywall Done, Tape & Mud | Oct 28
13 to 18 | Drywall Hanging In Progress | Nov 10
19 to 24 | MEP Complete, Drywall Next | Nov 25
CREW & CONTACTS
Crew Lead:
Hector Vega, 908-555-0378
Active Workers:
18 on site (12 drywall, 6 finishing)
Subcontractor (MEP):
Eastern NJ Mechanical, pending final punch
Subcontractor (Electric):
Ironbound Electric, sign-off Oct 8
Deliveries This Week:
Drywall compound · Fri Oct 2
Next Inspection:
Framing complete, Oct 1 ✔
Superintendent:
Tony Rizzi
Director:
Frank Delmonico
All figures as of October 1, 2026 · Turner Construction Newark Regional Office

## Slide 5
Schedule Risk & Budget Snapshot
SCHEDULE RISKS
Risk | Likelihood | Mitigation
Winter weather affecting Dec 9 pour | Medium | Pre-positioned tarp & heat blankets
Subcontractor punch-list delay (MEP) | Low | Written deadline: Oct 15
Material delivery slip (finish goods) | Low | Two-week buffer order placed
Inspection sign-off lag | Low | Pre-inspection walkthrough Oct 28
BUDGET SNAPSHOT
Category | Budget | Spent | Remaining
Labor | $3,200,000 | $2,810,000 | $390,000
Materials | $4,100,000 | $3,520,000 | $580,000
Subcontractors | $1,500,000 | $1,210,000 | $290,000
Contingency (5%) | $470,000 | $140,000 | $330,000
TOTAL | $9,270,000 | $7,680,000 | $1,590,000
KEY UPCOMING DATES
Date | Event | Owner
Oct 1, 2026 | City structural framing inspection (9:00 AM) | L. Reyes + Hector Vega
Oct 8, 2026 | Ironbound Electric final sign-off | Subcontractor
Oct 15, 2026 | MEP punch-list deadline | Eastern NJ Mechanical
Nov 17, 2026 | CS License CE credits deadline (Lisa) | L. Reyes (personal)
Dec 9, 2026 | Final concrete pour, 5:00 AM start | L. Reyes on site
Dec 18, 2026 | Completion walkthrough with client, 10:00 AM | L. Reyes + T. Rizzi

## Slide 6
Foreman Notes & Next Steps
Dec 9 pour is the critical-path lock. Weather window is being monitored weekly.
Hector Vega is cleared to run site independently during Lisa's December 14 birthday window.
Union crew schedule is stable through November; Q4 dues confirmed for October first weekday.
Frank Delmonico briefed on budget trajectory; no change orders pending.
Lisa on site from 5:00 AM on Dec 9, all hands on concrete crew, no exceptions.
Walkthrough packet to client prepared by Dec 15.
Post-project debrief with Tony Rizzi: week of Dec 22.
Turner Construction · Harrison Project · Q4 2026 · Foreman: Lisa Reyes