## Slide 1
TURNER CONSTRUCTION · NEWARK REGIONAL OFFICE
Downtown Newark Retail Renovation
Project Status Update · October 2026
Foreman: Lisa Reyes · Superintendent: Tony Rizzi
Site: Market Street Corridor, Newark, NJ
Contract Value: $2.1 Million · Active Since: February 2026

## Slide 2
Project Scope
Structural
Remove interior load-bearing wall; install W14×53 steel beam with new footings
Storefront
Full storefront replacement, aluminum curtain wall system, three entry vestibules
Interior Fit-Out
Drywall, paint, polished concrete floors, approx. 6,200 sq ft
MEP Upgrade
100A → 400A service upgrade; new HVAC split systems (4 zones); plumbing rough-in
Accessibility
ADA-compliant restrooms, ramps, signage, city permit 2026-NWK-0417
Façade
Brick tuck-pointing, cornice repair, new exterior lighting
Client: Market Street Partners LLC · Architect: Ironside Design Group, Newark

## Slide 3
Work Completed to Date
Stage 1
Site prep and asbestos abatement completed; permits cleared
Stage 2
Existing storefront and interior demo complete
Stage 3
Load-bearing wall removed; W14×53 beam installed and inspected
Stage 4
New footings poured; framing and rough carpentry complete
Stage 5
Electrical service upgrade 100A → 400A, NJ PSE&G coordinated
Stage 6
MEP rough-in complete; passed city rough-in inspection on schedule
Stage 7
Drywall hanging 80% complete; storefront curtain wall delivered
Overall Progress: ~78% Complete · No lost-time incidents to date

## Slide 4
Remaining Work & Open Items
REMAINING WORK
Oct to Nov
Drywall finish, tape, mud, and paint
Oct to Nov
Storefront curtain wall installation (2 weeks)
Nov
Polished concrete floors, sections 1 and 2
Nov
HVAC split-system installation (4 zones)
Nov to Dec
ADA restroom fit-out and accessible ramp
Dec
Exterior brick tuck-pointing and lighting
Dec
Punch-list and final clean
Dec
Certificate of Occupancy walk, city inspector
OPEN ITEMS / CHANGE ORDERS
CO-04
OPEN
Client requested marble tile upgrade, awaiting pricing
CO-05
OPEN
Additional ADA signage scope, $4,200 pending approval
RFI-12
OPEN
Curtain wall anchor detail, Ironside Design response due Oct 7
RFI-14
OPEN
HVAC condensate routing, subcontractor waiting on architect
INSP
SCHED
Final framing inspection scheduled Oct 28
INSP
SCHED
CO inspection tentative December 12
Projected Completion: December 2026 · Client Final Handover: December 19, 2026

## Slide 5
Budget vs. Actuals
Category | Contract Budget | Spent to Date | % Used | Forecast at Complete
Demo & Abatement | $85,000 | $82,400 | 97% | $85,000
Structural / Steel | $310,000 | $304,500 | 98% | $310,000
Rough Carpentry / Frame | $220,000 | $198,000 | 90% | $220,000
MEP (Electrical) | $340,000 | $310,000 | 91% | $340,000
MEP (Plumbing / HVAC) | $290,000 | $180,000 | 62% | $290,000
Storefront / Glazing | $185,000 | $142,000 | 77% | $185,000
Drywall / Finishes | $220,000 | $95,000 | 43% | $220,000
Floors (Polished Conc.) | $80,000 | $0 | 0% | $80,000
ADA / Accessibility | $75,000 | $22,000 | 29% | $79,200
Exterior Façade | $145,000 | $38,000 | 26% | $145,000
Contingency (10%) | $210,000 | $47,600 | 23% | $210,000
TOTAL | $2,160,000 | $1,419,500 | 66% | $2,164,200
Forecast at Complete: $2,164,200, within contingency. CO-04 marble upgrade excluded pending approval.

## Slide 6
Next Steps & Owner Actions
Oct 7, 2026
Ironside Design to respond on RFI-12 curtain wall anchor detail
Oct 8, 2026
L. Reyes reviews CO-04 marble upgrade pricing with client
Oct 15, 2026
Curtain wall installation begins, Hector Vega to oversee
Oct 28, 2026
Final framing inspection, L. Reyes on site
Nov 1, 2026
HVAC installation kickoff, all four zones
Nov 15, 2026
Polished concrete floor pour, sections 1 and 2
Dec 12, 2026
CO pre-inspection walkthrough, city inspector
Dec 19, 2026
Final handover to client, Market Street Partners LLC
Turner Construction · Downtown Newark Retail Renovation · Foreman: Lisa Reyes