# NOAA SEA GRANT PROGRAM

Hawaii Sea Grant College Program

University of Hawaii at Manoa

────────────────────────────────────────────────────────────────────────

# PROJECT TITLE:

Extension of the Kaneohe Bay Coral Resilience Study: Long-Term Recovery Monitoring

in a Climate-Stressed Reef System (Years 4 and 5)

────────────────────────────────────────────────────────────────────────

Principal Investigator:    Lorraine Roach, M.S.

Marine Conservation Biologist

Coral Futures Institute

45 Kaneohe Bay Drive, Suite 200

Kaneohe, HI 96744

l.roach@coralfuturesinstitute.org

(808) 555-0210

Co-Investigator:           Dr. Leilani Kamaka, Ph.D.

Director, Coral Futures Institute

45 Kaneohe Bay Drive, Suite 200

Kaneohe, HI 96744

l.kamaka@coralfuturesinstitute.org

Requested Amount:          $85,000 per year for two years (total $170,000)

Project Period:            October 2026 through September 2028

────────────────────────────────────────────────────────────────────────

# ABSTRACT

Kaneohe Bay experienced a severe mass bleaching event in 2022, reducing coral cover

across monitored sites by an average of 41%. The ongoing three-year resilience study

has documented consistent recovery trajectories at four of five study sites, with mean

coral cover increasing from 18.1% in the immediate post-bleach period to 31.4% by Year 3.

This proposal requests a two-year extension to continue longitudinal monitoring,

characterize genus-level thermal tolerance variation across depth gradients, and quantify

the effectiveness of community-based monitoring as a scalable conservation tool. The

extended study will add two new sites to the monitoring network and integrate volunteer

data from the Community Reef Monitoring Program into a standardized reef health index

applicable to reef management across the Hawaiian archipelago. Findings will directly

inform Marine Protected Area management decisions by the Division of Land and Natural

Resources and contribute to NOAA Pacific climate adaptation strategies under the

National Coral Reef Monitoring Program framework.

────────────────────────────────────────────────────────────────────────

# PROBLEM STATEMENT

Climate-driven coral bleaching events are increasing in frequency and severity across the

Indo-Pacific, and Hawaii is not exempt from this trajectory. Sea surface temperatures in

the central Pacific have exceeded the bleaching threshold for Hawaii reef systems with

growing regularity, and multi-year bleaching sequences reduce the interbleaching recovery

time that coral populations require to rebuild structural complexity and reproductive

capacity. Kaneohe Bay, as one of the most extensively studied reef systems in the Pacific

and a bay with significant ecological, cultural, and economic value to the people of Oahu,

provides a critical natural laboratory for understanding the mechanisms and rates of coral

recovery following mass bleaching disturbance. The reef communities of Kaneohe Bay support

commercial and subsistence fisheries, serve as a training ground for a generation of

Hawaiian marine scientists, and hold deep cultural significance for Native Hawaiian

communities whose relationship with the Bay extends across many generations. Without

continued systematic monitoring, the three-year longitudinal dataset collected under the

current grant will be insufficient to characterize full post-bleach recovery trajectories,

distinguish resilient from vulnerable sites, or identify reef areas at elevated risk during

the next thermal stress event. The window for collecting uninterrupted recovery data closes

if monitoring ceases before full recovery is achieved or before the next bleaching event

disrupts the baseline.

────────────────────────────────────────────────────────────────────────

# PRIOR WORK: YEARS 1 THROUGH 3 KEY FINDINGS

The following results were produced under the current Hawaii Sea Grant award and form the

evidentiary foundation for this extension request:

Mean coral cover across five monitored sites increased from 18.1% (2022 post-bleach

baseline) to 31.4% by the end of Year 3, with recovery rates varying substantially

by site and by genus.

Sites KNB-01, KNB-02, KNB-04, and KNB-05 showed consistent recovery trajectories.

Site KNB-03 (Heeia Channel Fringe) diverged significantly beginning in Year 2.

Thermal stress correlation analysis confirmed that colonies at depths below 5 meters

experienced 2.2 to 3.7 degree-weeks less cumulative thermal stress during the 2022

event compared to shallow counterparts, and show correspondingly higher survival rates.

An anomalous crown-of-thorns starfish (Acanthaster planci) aggregation was documented

at KNB-03 beginning in October 2025, identified first by community program volunteers

before the research team's scheduled dive. The aggregation has suppressed recovery at

that site and is being monitored monthly.

The Community Reef Monitoring Program expanded from one pilot site to three active

community-monitored sites, with 14 trained volunteers contributing 68 survey events

in Year 3.

Preliminary findings were included in a Pacific MPA management policy brief submitted

to NOAA's Coral Reef Conservation Program and the Hawaii DLNR Division of Aquatic

Resources in December 2025.

────────────────────────────────────────────────────────────────────────

# PROPOSED RESEARCH: YEARS 4 AND 5

Year 4 (October 2026 through September 2027)

Year 4 objectives center on completing the recovery characterization for the five original

study sites while expanding the monitoring network. Full recovery, defined here as mean

coral cover returning to within 10% of pre-bleach 2021 values, is projected to occur

between Year 4 and Year 5 at KNB-01 and KNB-02 based on current trajectory models.

Continued monitoring is essential to confirm these projections and to determine whether

KNB-03 will recover under crown-of-thorns pressure or require intervention. In Year 4,

we will expand genus-level thermal tolerance analysis to include Montipora, Porites, and

Pocillopora at three depth classes (1 to 3m, 4 to 7m, and 8 to 12m), enabling

genus-specific vulnerability indices relevant to climate scenario planning. Two new sites,

KNB-06 and KNB-07, will be added to the monitoring network in Year 4, bringing the total

to seven sites. These sites were selected in consultation with Keoni Mahoe and DLNR based

on their proximity to Heeia Fishpond and their potential value as reference areas for

evaluating land-based stressor interactions with bleaching recovery.

Year 5 (October 2027 through September 2028)

Year 5 will integrate all available data streams, including transect, photo-quadrat,

thermal logger, and community volunteer records, into a standardized reef health index

developed collaboratively with DLNR and NOAA representatives. The index will be designed

for broad applicability to reef monitoring programs across the Hawaiian Islands. A

peer-reviewed manuscript presenting full recovery trajectory data across six years of

monitoring will be drafted in Year 5 and submitted to Coral Reefs or Marine Ecology

Progress Series. A complete synthesis will be presented at the Pacific Islands Climate

Adaptation Science Center conference. Community monitoring protocols refined during

Years 4 and 5 will be packaged as a freely available training resource for replication

at other Hawaii reef monitoring sites.

────────────────────────────────────────────────────────────────────────

# METHODS

All existing survey protocols will continue unchanged in Years 4 and 5 to maintain

time-series integrity. Belt transect surveys (25m, 2m belt width, n=3 per site) and

photo-quadrat surveys (0.5m x 0.5m frame, 5m intervals, 6 per transect) will be conducted

monthly at five primary sites and quarterly at KNB-06 and KNB-07. Beginning in October

2026, HOBO Tidbit temperature loggers will be deployed at three depth strata at two

thermally contrasting sites (KNB-02 and KNB-07), logging at 15-minute intervals, to build

a continuous thermal exposure record linking in-situ temperature to observed coral response.

The Community Reef Monitoring Program will be expanded to include two additional community

groups, with formal volunteer training events beginning October 2026. Volunteer training

will follow the updated Community Reef Monitoring Program Training Manual (Version 2.1,

January 2026). Community survey data will be quality-controlled against concurrent

research-team surveys at shared sites before inclusion in the combined dataset.

────────────────────────────────────────────────────────────────────────

# BUDGET NARRATIVE

Year 1 - Total Request: $85,000

Personnel:

Lorraine Roach, M.S. (Principal Investigator, 75% FTE)           $46,500

Field Research Assistant (25% FTE, 12-month appointment)         $12,000

Personnel Subtotal                                               $58,500

Equipment:

HOBO Tidbit v2 temperature loggers (24 units at $180)             $4,320

Replacement underwater cameras and housings (2 units)             $1,800

Quadrat frames, transect hardware, dive equipment maintenance     $1,880

Equipment Subtotal                                                $8,000

Field Operations:

Research vessel time (boat rental and fuel, 48 survey days)       $6,400

Compressed air fills and nitrox fills                             $1,100

Equipment repair and replacement consumables                      $2,000

Field Operations Subtotal                                         $9,500

Indirect Costs (10.5% of direct costs):                             $9,000

Year 1 Total:                                                      $85,000

Year 2 - Total Request: $85,000

Personnel costs are similar to Year 1. Equipment costs are reduced by approximately

$3,500 as logger deployment hardware is already in place. The reduction is redirected

to publication and dissemination costs, including open-access publication fees

(estimated $2,500 for target journals), conference travel to the Pacific Islands Climate

Adaptation Science Center meeting (estimated $1,800 for two attendees), and community

curriculum printing and distribution ($800).

Year 2 Total:                                                      $85,000

Combined Two-Year Total:                                          $170,000

────────────────────────────────────────────────────────────────────────

# PROJECT TIMELINE

Oct 2026     Field expansion to KNB-06 and KNB-07. Temperature logger

deployment at KNB-02 and KNB-07. Community training cohort

recruitment begins.

Nov 2026     First volunteer training events for two new community groups.

Year 4 monitoring fully operational across all seven sites.

Jan 2027     Deep analysis of Years 1 through 3 data completed. Genus-level

thermal tolerance index draft framework delivered to DLNR.

Jun 2027     Mid-project review meeting with DLNR and NOAA collaborators.

Community monitoring protocol review and update.

Sep 2027     Year 4 data compilation and quality control complete.

Reef health index framework finalized with stakeholder input.

Jan 2028     Manuscript draft completed and submitted for co-investigator

and NOAA review before journal submission.

Apr 2028     Manuscript submitted to Coral Reefs or Marine Ecology Progress

Series. Conference abstract submitted.

Sep 2028     Final project report submitted to Hawaii Sea Grant. Volunteer

training resource package finalized and distributed. All data

archived with NOAA National Centers for Environmental Information.

────────────────────────────────────────────────────────────────────────

# BROADER IMPACTS

The community-based monitoring model developed and refined through this project is

directly replicable across Hawaii reef monitoring programs and, with adaptation,

applicable to reef systems throughout the Pacific. The training manual, field data

protocols, and quality-control procedures will be made freely available as a

downloadable resource through the Coral Futures Institute website and through the

Hawaii DLNR Division of Aquatic Resources extension network. Data collected through

both the research-team surveys and the community monitoring program will be shared with

NOAA, DLNR, and reef MPA management teams on an annual basis, enabling evidence-based

updates to management plans without delay. Training opportunities created through the

program expansion provide meaningful marine science engagement for Native Hawaiian

practitioners, students, and fishing community members who have a generational stake

in the health of Kaneohe Bay. The participation of community members as trained data

collectors, rather than passive stakeholders, reflects a conservation model grounded

in shared stewardship. On a broader scale, the longitudinal dataset produced by this

project will contribute to the Pacific climate adaptation evidence base at a moment

when long-term recovery data from well-characterized reef systems is urgently needed

to calibrate regional thermal stress models and restoration prioritization frameworks.

────────────────────────────────────────────────────────────────────────

End of Proposal

Submitted by: Lorraine Roach, M.S.

Institution:  Coral Futures Institute, Kaneohe HI 96744

Contact:      l.roach@coralfuturesinstitute.org

────────────────────────────────────────────────────────────────────────