## Slide 1
Fall Fundraiser
Grace Community Church, committee briefing
Saturday, November 14, 2026 | 10:00 AM to 3:00 PM, Fellowship Hall

## Slide 2
THE GOAL
What we are raising for
02
Fund the winter heating-assistance program and youth group travel.
Target
$6,500 net
Last fall
Cleared $5,900
Stretch
$7,500 with the raffle
Grace Community Church | Fall fundraiser

## Slide 3
TARGET
This year against last
03
Chart: 
| Last fall | This year target | Stretch goal
Net raised | 5900 | 6500 | 7500
Grace Community Church | Target

## Slide 4
STATIONS
The floor plan
04
Raffle table
Michelle, donated prizes, card reader.
Bake sale
Women's Group, banana bread and pies.
Coffee and cider
Youth Group, two dark-roast urns.
Handmade crafts
Vendors with signed agreements on file.
Plant stand
Garden Committee, herb starts.
Kids' corner
Sunday School, supervised activities.
Grace Community Church | Stations

## Slide 5
TIMELINE
The run-up
05
Oct 20
Confirm vendors, send agreements
Oct 31
Raffle prizes collected and logged
Nov 7
Print signage, final volunteer schedule
Nov 13
Hall setup, 4 to 6 PM
Nov 14
Doors 10 AM, raffle drawn 2:30, cleanup by 4
Grace Community Church | Timeline

## Slide 6
VOLUNTEERS
Who is where
06
Front entrance
Greeters and signups
Raffle
Michelle plus one
Hospitality
Coffee, cider, restock
Floaters
11 to 1 rush coverage
Setup crew
Friday evening, tables
Cleanup
Saturday, by 4 PM
Grace Community Church | Volunteers

## Slide 7
SUPPLIES
What to secure
07
Folding tables
20 needed, borrow 6 from Grace
Folding chairs
60, all on hand
Tablecloths
20 needed, short 8, pick up more
Water cases
10 needed, short 6
Directional signage
Print run from the Figma file
First-aid kits
Two, currently one
Grace Community Church | Supplies

## Slide 8
VENDORS
Tables and agreements
08
• All vendor tables carry a signed agreement on file before the day.
• Vendor fees and donations recorded at the card terminal.
• Reconcile the terminal the Monday after the event.
• Thank-you notes to the table-lending churches by November 14.
Grace Community Church | Vendors

## Slide 9
DAY OF
November 14 schedule
09
7:30 AM
Setup crew and hospitality in
8:00 AM
Tables dressed, raffle staged
10:00 AM
Doors open
11:00 to 1:00
Peak traffic, floaters on
2:30 PM
Raffle drawn
3:00 to 4:00
Close and cleanup
Grace Community Church | Day of

## Slide 10
Showing up is the work.
Thank you to every volunteer, baker, and donor. A warm hall keeps a neighbor warm this winter.