## Slide 1
Thesis Committee Progress Review
Effects of ocean warming on intertidal invertebrate community composition in Puget Sound
Alex Santos | M.S. Marine Biology | Puget Sound Institute of Science
Progress meeting, January 22, 2027 | Committee: Dr. Sarah Lindstrom, Dr. Marcus Hull

## Slide 2
Where things stand
Field done
All 2025 survey data entered, cross-checked, and locked
Analysis
NMDS, PERMANOVA, and diversity indices complete in R
Writing
Chapter 3 drafted, Chapter 4 in progress
Since the last check-in I locked the survey database with Yolanda, finished the Site 7 thermal-gradient analysis, and circulated a Chapter 3 results draft to Dr. Lindstrom.
This meeting is to confirm framing on the central result and agree the path to a spring 2027 defense.

## Slide 3
Chapter status
Chapter | Status | Next action
1 Introduction | Complete | Light edit after results lock
2 Methods | Complete | Add evenness metric description
3 Results | Full draft with advisor | Address S.L. comments, finalize tables
4 Discussion | In progress | Place results in Salish Sea warming context
5 Conclusion | Outline | Draft after Chapter 4

## Slide 4
The central result
Chart: Diversity declines as mean site temperature rises (deg C)
| 11.2 | 11.8 | 12.4 | 13.1 | 13.9 | 14.6 | 15.2 | 15.8
Shannon diversity (H) | 2.41 | 2.33 | 2.21 | 2.07 | 1.95 | 1.81 | 1.72 | 1.62
Eight-site survey, southern Puget Sound.
Shannon, Simpson, and evenness all fall along the thermal gradient.
Site 7 (Titlow) remains the focal comparison site for Chapter 3.

## Slide 5
Open questions for the committee
How hard should Chapter 4 lean on a single-season result before the multi-year data lands?
Is the eight-site diversity gradient worth a short standalone section, or a figure inside Chapter 3?
Target the spring 2027 defense window, or build in a buffer for the chemistry covariate work?