# IRB Study Monthly Summary Report - November 2026

# Study

Culturally Adapted Dietary Interventions for T2DM

# Enrollment Status

Target: 60 participants (30 intervention 30 control)

Currently enrolled: 12

Screening pipeline: 8 additional pending consent

Dropout rate: 0%

# Intervention Delivery

Sessions delivered this month: 18

Average session length: 52 minutes

Completion rate: 94%

Common topics: carbohydrate counting with traditional foods family meal adaptation

# Observations

Food insecurity in enrolled sample: 43%

Average baseline A1C: 8.7%

Engagement score: 8.2 out of 10

100% of intervention participants identified at least one traditional food they could retain

# Data Management

All data de-identified upon collection

Stored securely with Dr. Adler access

IRB consent forms in an e-signature service

No adverse events or protocol deviations

# Next Month Goals

Enroll 8 additional participants to reach n=20 by December end

Deliver 3-month follow-up sessions for first 8 participants

Prepare FNCE abstract draft for February 2027 deadline