## Event Budget
Cuts Before Christmas, December 19, 2026, Sharp Line Cuts
Category | Item | Vendor | Qty | Unit Cost | Line Total | Status | Notes | Task | Owner | Due Date | Done
Catering | Taco plates | El Sol Kitchen | 75 | 10 | 750 | Confirmed | 75 plates for walk-in guests | Confirm DJ Rel availability | James | Nov 15, 2026 | Yes
Catering | Horchata gallons | El Sol Kitchen | 3 | 15 | 45 | Confirmed |  | Order Pinnacle samples | James | Nov 20, 2026 | Yes
Catering | Jamaica gallons | El Sol Kitchen | 2 | 15 | 30 | Confirmed |  | Design flyers | Ty | Nov 25, 2026 | Yes
Catering | Churros dozens | El Sol Kitchen | 3 | 18 | 54 | Confirmed |  | Print and distribute flyers | Andre | Dec 1, 2026 | No
Giveaways | Pinnacle pomade samples | Pinnacle Barber Supply | 60 | 4.2 | 252 | Ordered | 3 oz tins | Confirm El Sol Kitchen catering | James | Dec 5, 2026 | No
Giveaways | Beard oil samples | Pinnacle Barber Supply | 60 | 5.1 | 306 | Ordered | 4 oz bottles | Set up social media promo | Darius | Dec 8, 2026 | No
Giveaways | Custom combs | Ty Jackson (handmade) | 25 | 3 | 75 | In Progress | Ty's combs with shop logo | Order banners from local print shop | James | Dec 10, 2026 | No
Music | DJ rental | DJ Rel | 1 | 200 | 200 | Booked | 4 hour set | Buy balloons, towels, drinks | Ty | Dec 15, 2026 | No
Music | Sound system rental | Motor City Audio | 1 | 150 | 150 | Booked | Speakers and mic | Decorate shop | All Staff | Dec 18, 2026 | No
Decorations | Banner printing | local print shop | 2 | 42.5 | 85 | Pending | Outdoor and indoor banners | Day-of setup and sound check | James, DJ Rel | Dec 19, 2026 | No
Decorations | Balloons and supplies | general store | 1 | 40 | 40 | Pending
Marketing | Flyers 200ct | copy center | 1 | 70 | 70 | Printed | Distribute at nearby businesses
Marketing | social media promo | social media advertising | 1 | 50 | 50 | Scheduled | Geo-targeted to 48221 zip
Misc | Extra towels | wholesale club | 2 | 15.99 | 31.98 | Pending | Pack of 12 each
Misc | Water and drinks | warehouse store | 1 | 45 | 45 | Pending | Bottled water and pop
Misc | Cleanup supplies | general store | 1 | 20 | 20 | Pending | Trash bags, wipes
TOTAL |  |  |  |  | 2203.98