Perez Textile Conservation

47 Pond Street (Ground Floor Studio), Jamaica Plain, MA 02130  |  (617) 555-3800

TREATMENT PLAN AND PROPOSAL

Collection: Twenty two American needlework samplers, 1750 to 1850

Client: Claire Pemberton, Curator of American Decorative Arts, Peabody Essex Museum

Studio project number: PTC-2025-008     Plan date: February 5, 2026

Companion document: PEM Sampler Condition Survey (delivered January 30, 2026)

1. Scope

Following the condition survey of the twenty two samplers, this plan groups the collection into three treatment tiers and sets a sequence that allows the most fragile pieces to be stabilized first. The full written survey report is due to the Peabody Essex Museum on January 15, 2027.

2. Treatment tiers

Tier A, immediate stabilization (7 samplers).

Active losses, brittle silk, or failing prior mounts. These receive humidification, realignment, and a stitched support before any handling for study or display.

Tier B, standard stabilization (10 samplers).

Sound but soiled or slightly distorted. Surface cleaning by low suction through screen, minor stitched support, and rehousing.

Tier C, rehousing only (5 samplers).

Stable and clean. These need archival rehousing and updated condition photography, no intervention to the textile itself.

3. Methods and ethics

All treatment is minimal and reversible. No overpainting, no replacement of lost stitching, no bleaching.

Supports are fine silk or polyester crepeline, stitched with conservation grade silk thread.

Each sampler is documented before, during, and after, with raking light and normal light images.

4. Schedule and reporting

Treatment runs from October 2026 through the first week of January 2027, with a written report and updated photography delivered to the museum by January 15, 2027. Progress notes will be shared at the end of October and the end of November 2026.

Prepared by Jesse Perez, Perez Textile Conservation