## Slide 1
MUSEUM OF FINE ARTS, BOSTON
Project PTC-2024-031 - Conservation Planning
OTTOMAN EMBROIDERY SUITE
Exhibition Planning - Conservation Progress
6 Panels
17th-18th Century
Exhibition Target
December 5, 2026
Conservator
Jesse Perez
Institutional Contact
Dr. Elena Vasquez
Internal planning document for conservation treatment status, timeline, and installation requirements. For review by the conservation department and curatorial team. February 2026.
Perez Textile Conservation - 47 Pond Street, Jamaica Plain, Boston MA 02130 - (617) 555-3800

## Slide 2
Jesse Perez | Perez Textile Conservation | Jamaica Plain, Boston
OBJECT INVENTORY
Six-Panel Suite - Material and Condition Summary
Panel | Accession | Century | Dimensions (cm) | Ground | Embroidery | Condition | Treatment Phase
Panel 1 | 2024.1583.1 | 17th | 62 x 84 | Linen tabby | Silk + metallic | Good | Stabilized
Panel 2 | 2024.1583.2 | 17th | 58 x 79 | Linen tabby | Silk couched | Good | Stabilized
Panel 3 | 2024.1583.3 | 18th | 71 x 94 | Cotton plain | Silk polychrome | Fair | Stabilized
Panel 4 | 2024.1583.4 | 18th | 64 x 89 | Linen tabby | Silk + silver-gilt | Fair - warp damage | In treatment
Panel 5 | 2024.1583.5 | 18th | 55 x 72 | Linen twill | Silk geometric | Fair | In treatment
Panel 6 | 2024.1583.6 | 18th | 48 x 62 | Cotton plain | Silk floral | Poor - soiling | Humidification

## Slide 3
Jesse Perez | Perez Textile Conservation | Jamaica Plain, Boston
TREATMENT PROGRESS
Panel-by-Panel Completion and Next Steps
Panel 1 - 2024.1583.1
Complete - mounted
100%
Panel 2 - 2024.1583.2
Complete - mounted
100%
Panel 3 - 2024.1583.3
Complete - mounted
100%
Panel 4 - 2024.1583.4
Warp repair in progress
62%
Panel 5 - 2024.1583.5
Cleaning + structural survey
50%
Panel 6 - 2024.1583.6
Humidification phase
20%

## Slide 4
Jesse Perez | Perez Textile Conservation | Jamaica Plain, Boston
TIMELINE
Treatment and Installation Schedule to December 2026
Feb 2026
Panels 1-3 mounted
Oct 2026
Panel 4-5 treatment complete
Oct 24, 2026
MFA planning meeting
Nov 2026
Final mounting all 6 panels
Dec 1, 2026
Delivery to MFA install team
Dec 5, 2026
Exhibition opens Private preview
Key Dates
October 24, 2026
MFA exhibition planning meeting with Dr. Elena Vasquez - mount review
November 11-14, 2026
Conservator at AIC Annual Meeting, Salt Lake City - studio contact: Samuel Okafor
November 20-30, 2026
Final mounting phase - all six panels installed on exhibition boards
December 1, 2026
All mounts delivered to MFA installation team
December 5, 2026
Exhibition opening - Ottoman Embroidery Suite

## Slide 5
Jesse Perez | Perez Textile Conservation | Jamaica Plain, Boston
ENVIRONMENTAL SPECIFICATIONS
Required Display and Storage Conditions
TEMPERATURE
19-21 degrees C
Stable within 1 degree C per day. Silk thread contracts and distorts under thermal cycling.
RELATIVE HUMIDITY
48-52% RH
No excursion above 58% or below 42%. Monitor continuously during exhibition run.
LIGHT LEVEL
50 lux maximum
UV filtered. No fiber optic substitution. Metallic thread is reflective; no direct spot at less than 45 degrees.
LIGHT EXPOSURE
50,000 lux-hours/year total
Assume 200 lux-hours/day if open 8 hours. Close before reaching annual limit.
AIR MOVEMENT
No direct airflow to panels
Textile oscillation from HVAC causes long-term warp fatigue. Diffuse airflow only.
VIBRATION
Minimal - no adjacent mechanical
Panel frames bolted at 4-point minimum. No panels on walls shared with HVAC units.

## Slide 6
Jesse Perez | Perez Textile Conservation | Jamaica Plain, Boston
BUDGET
Conservation Fee Summary and Project Accounting
Invoice | Date | Phase | Amount
PTC-INV-2025-042 | Oct 2025 | Condition assessment + report | $3,200
PTC-INV-2025-051 | Nov 2025 | Treatment phase 1 - Panels 1-3 | $9,400
PTC-INV-2026-014 | Jan 2026 | Treatment phase 2 - ongoing | $7,850
PTC-INV-2026-031 | Feb 2026 | Panel 4 warp repair (in progress) | $4,200
[Pending] | Oct 2026 | Panel 5 + Panel 6 treatment | Est. $7,600
[Pending] | Nov 2026 | Final mounting - all 6 panels | Est. $4,800
Chart: Fee Distribution by Phase (USD)
| Assess. | Phase 1 | Phase 2 | Ongoing | Pending
Fee (USD) | 3200 | 9400 | 7850 | 4200 | 12400
Total contracted: $37,050 Paid to date: $24,650 Balance remaining: $12,400

## Slide 7
Jesse Perez | Perez Textile Conservation | Jamaica Plain, Boston
NEXT STEPS
Outstanding Actions and Responsibilities
Jesse Perez
Complete Panel 4 warp repair - target February 28, 2026
Begin Panel 5 surface cleaning and structural stabilization
Draft updated treatment timeline for Elena Vasquez review
Dr. Elena Vasquez / MFA
Confirm exhibition case dimensions by April 2026
Arrange environmental monitor installation in gallery
Coordinate October 24 planning meeting with curatorial team
MFA Installation Team
Provide wall-load specifications for six panel mounts
Schedule crating and transit window for December 2026
Confirm lighting rig type and UV filter installation