## Slide 1
PEABODY ESSEX MUSEUM
Salem, Massachusetts
PROJECT PTC-2025-008
AMERICAN SAMPLER COLLECTION
Condition Survey and Treatment Planning Report
Jesse Perez, Conservator
Perez Textile Conservation Jamaica Plain, Boston, MA 02130 February 2026
Prepared for: Claire Pemberton Curator of American Decorative Arts
22
Samplers surveyed
1750-1850
Period covered
7
Tier A - urgent treatment
Jan 15, 2027
Report due date
Perez Textile Conservation - Project PTC-2025-008 - Condition Survey Report

## Slide 2
PTC-2025-008 | Peabody Essex Museum - Sampler Survey | Jesse Perez
METHODOLOGY
Examination Protocol for the 22-Sampler Survey
Fiber identification
Visual microscopy at 10x and 40x magnification. Fiber mount slides for ambiguous cases. Documented by accession number.
Dye assessment
UV fluorescence and spot test where condition permits. Documented by fiber group (silk, wool, linen ground).
Structural survey
Thread count (warp and weft), embroidery stitch types, ground weave, and physical condition by quadrant. Condition categories: Stable, At-Risk, Failing, Urgent.
Dimensional record
Width, height, and depth of any planar distortions measured. All measurements in centimeters.
Photographic record
Raking light (2 directions), transmitted light, UV fluorescence. All images tagged with accession number.
Triage and tiering
Each object assigned to Tier A (treatment urgently required), Tier B (treatment within 5 years), or Tier C (monitor only).

## Slide 3
PTC-2025-008 | Peabody Essex Museum - Sampler Survey | Jesse Perez
RESULTS OVERVIEW
Condition Distribution Across 22 Samplers
Chart: Condition Tier Distribution
| Tier A - Urgent | Tier B - Priority | Tier C - Monitor
Count | 7 | 10 | 5
Condition Issue | Objects | Tier
Active warp breakage | 4 | A
Severe soiling / grime penetration | 3 | A
Significant embroidery loss | 5 | B
Localized planar distortion | 7 | B
Surface dust / minor soiling | 5 | B/C
Stable, no active issues | 3 | C
Historic repair (reversible needed) | 2 | B

## Slide 4
PTC-2025-008 | Peabody Essex Museum - Sampler Survey | Jesse Perez
PRIORITY OBJECTS
Tier A - Seven Objects Requiring Urgent Treatment
Accession | Date | Dimensions (cm) | Ground | Primary Issue | Proposed Treatment | Est. Cost
PEM.1996.014.001 | c. 1750 | 28 x 34 | Linen | Warp breakage, 18% | Linen thread support, humidification | $1,800
PEM.2001.022.004 | c. 1780 | 22 x 29 | Linen | Active warp loss, upper 1/4 | Thread replacement, stabilization | $2,100
PEM.2008.031.002 | c. 1800 | 31 x 41 | Linen | Warp breakage + soiling | Cleaning, consolidation | $2,400
PEM.1974.008.001 | c. 1765 | 18 x 24 | Cotton | Heavy grime, fiber distortion | Surface clean + humidification | $1,650
PEM.1988.014.003 | c. 1790 | 25 x 32 | Linen | Severe planar distortion | Humidification + re-lay | $1,950
PEM.2012.044.001 | c. 1820 | 29 x 38 | Linen | Embroidery loss, 20% | Stabilization, no restoration | $1,700
PEM.2015.031.002 | c. 1845 | 34 x 44 | Cotton | Ground tear, embroidery loose | Stitch consolidation, support | $2,200

## Slide 5
PTC-2025-008 | Peabody Essex Museum - Sampler Survey | Jesse Perez
MATERIAL ANALYSIS
Fiber and Dye Distribution Across Collection
Chart: Objects by Period and Ground Fiber
| 1750-1770 | 1771-1790 | 1791-1810 | 1811-1830 | 1831-1850
Linen ground | 2 | 5 | 6 | 5 | 4
Wool embroidery present | 2 | 4 | 5 | 4 | 3
Chart: Embroidery Thread Material (22 objects)
| Wool thread | Silk thread | Cotton thread | Mixed
Count | 14 | 5 | 2 | 1

## Slide 6
PTC-2025-008 | Peabody Essex Museum - Sampler Survey | Jesse Perez
BUDGET AND TIMELINE
Phased Treatment Plan and Estimated Costs
Chart: Budget by Treatment Phase (USD)
| Tier A (7 obj.) | Tier B (10 obj.) | Tier C (5 obj.) | Framing All 22
Estimated Cost (USD) | 13800 | 18500 | 4500 | 11000
Phased Schedule
Phase 1
Feb - Oct 2026
Tier A treatment (7 objects)
$13,800
Phase 2
Oct - Dec 2026
Tier B priority (10 objects)
$18,500
Phase 3
Jan - Apr 2027
Tier C monitoring + framing all
$15,500
Condition Report
Jan 15, 2027
Full written report delivered
Included
Total estimated: $47,800 (subject to revision after Phase 1 reassessment)

## Slide 7
PTC-2025-008 | Peabody Essex Museum - Sampler Survey | Jesse Perez
RECOMMENDATIONS
Key Conservation Guidance for the Collection
Environmental Priority
Reduce storage RH from current 55-58% to 48-52%. The linen grounds in this collection are stress-fractured in several objects at the current conditions. A 2-degree Celsius drop and RH stabilization will slow further degradation significantly.
Immediate Treatment
Four objects in Tier A show active warp breakage. These should be moved to priority treatment in the first half of 2026 before the structural situation worsens under normal handling.
Handling Protocol
No object in the collection should be handled without a foam-padded tray beneath and a conservator or trained collections manager present. Several ground fabrics are fragile enough that a dropped edge could be catastrophic.
Storage Review
Eight objects are currently stored folded. All should be rolled on archival tubes or stored flat with Hollytex interleaving. Folding is the most common mechanical damage vector in this type of collection.
No Cosmetic Restoration
None of the 22 objects requires or would benefit from aesthetic restoration. The losses are part of the historical record. Stabilization and structural support are the appropriate goals throughout.