## Tasks
Task ID | Task | Owner | Due | Status | Notes
T-01 | Confirm Hamilton Community Hall booking | Devon Pratt | 2027-03-06 | Done | Warming kitchen included
T-02 | Draft retreat agenda | Ben Marshall | 2027-03-10 | In progress | Review with Pastor Crawford
T-03 | Circulate pre-read packet | Ben Marshall | 2027-03-20 | Not started | Draft only; nothing sends
T-04 | Volunteer rota for event days | Deborah Kessler | 2027-03-24 | In progress | Coverage for both spring events
T-05 | Accessibility check (ramps/ASL) | Anthony Delgado | 2027-03-18 | In progress | Quiet room + seating
T-06 | Pull prior-cycle analytics | Gabriel Osei | 2027-03-15 | In progress | Traffic + drop-off, report only
T-07 | Advance volunteer applications | Ben Marshall | 2027-03-12 | Not started | Route to Pastor Crawford

## Timeline
Milestone | Date | Owner | Notes
Pre-retreat committee meeting | 2027-03-18 | Pastor Crawford | Fellowship Room B
Pre-read packet due | 2027-03-20 | Ben Marshall | Three drafts in hand
Spring Outreach Retreat | 2027-03-27 | Committee | 9 AM - 1 PM, Hamilton Community Hall
Spring Community Meal (tentative) | 2027-04-17 | Louis Ferreira | Confirm on Eventbrite
Health & Wellness Fair (tentative) | 2027-05-15 | Priya Ramaswamy | Venue TBD; confirm before promoting

## ReadMe
About this tracker
Logistics planning only. Not the system of record and not for FY close.
No financial figures live here - money is reconciled in the official ledgers.
Partner statuses are NOT decided here; defer to Salesforce + signed agreements.
Nothing sends or publishes from this file. Drafts stay drafts until Ben sends.
Timezone: America/New_York.