## Renovation Budget
Item | Vendor | Budgeted | Actual | Paid Date | Status | Notes
Roof Repair north wing | Gulf Coast Roofing | 8500 | 8200 | Oct 14 2025 | Paid | Completed ahead of schedule
Interior Paint sanctuary | Brother Marcus volunteer | 0 | 0 | N/A | Planned Nov 7 2026 | Paint donated by Harrison Hardware
Fellowship Hall Flooring | Biloxi Floor Coverings | 4200 | 4315 | Nov 3 2025 | Paid | LVP tile installed
HVAC Filter Replacement | Comfort Air HVAC | 380 | 380 | Jan 15 2025 | Paid | Quarterly scheduled maintenance
Parking Lot Striping | Coastal Line Striping | 750 | 695 | Feb 18 2025 | Paid | Handicap spaces updated
Sound System Upgrade | SoundWave Electronics | 3200 | 0 | TBD | Approved/Not Started | Fundraising ongoing
Exterior Painting | Powell Brothers Painting | 2800 | 0 | TBD | Approved/Not Started | Coordinated with paint donation
Stairway Handrail | Biloxi Iron Works | 920 | 920 | Oct 28 2025 | Paid | Safety code compliance
Nursery Cabinets | John Baker volunteer | 0 | 145 | Nov 12 2025 | Paid - Materials only | John built donated labor
Landscaping and Mulch | Harrison County Nursery | 410 | 398 | Oct 5 2025 | Paid | Front garden beds

## Fund Tracker
Source | Amount | Date Received | Designated For
General Fund Allocation | 5000 | Jan 2025 | Operations
Summer Picnic Fundraiser | 2145 | Jul 2025 | Renovation
Special Offering Sep | 1890 | Sep 2025 | Renovation
Anonymous Donor | 1500 | Oct 2025 | Sound System
Building Fund Tithe | 3320 | Year-to-date 2025 | General Renovation