## Sheet
Item | Owner | Quantity | Status | Ready By | Note
Family folders | Kelly | 220 | To print | Nov 9 | Main office copier
HS course timeline handout | Kelly | 220 | Drafting | Nov 5 | Dr. Fredericks review first
Spanish handouts | Kelly and aide | 120 | To translate | Nov 6 | Bilingual aide confirmed
Crisis text line cards | Partridge | 250 | Have | Done | Restocked
Summer program flyer | Yuen | 150 | To print | Nov 9 | Trades focus
Sign-in clipboard (private) | Kelly | 1 | Have | Done | Kept by counselor, not on table
Table and 2 chairs | Facilities | 1 set | Requested | Nov 11 | Near main entrance
Water for staff | Kelly | 1 case | To buy | Nov 11 | Eat at 4:30